## Slide 1
FAE/AE Global Community
September 2022
Mazitova Elvira
ADMKD/ADMS/ADMS12 – Project Management
Automotive Business Unit
Renesas Electronics Corporation

## Slide 2: Agenda
Support structure for SoC and MCU, possible other products
General steps proposal in support structure enhancement
      Global FAE community

## Slide 3
Support structure general overview – to continue working
SoC
2. MCU
3. Analog
Application
Sensor
Video
4. Power
L1 FAE+FAE Deputy
App Eng
(TPS)
L2 App Eng
(FDT)
L3 SWDD
ASDD
RECN
REA REIN REL
REE
TPS_team_SoC
FDT_X
FDT_Z
…
i1.2 Direct ticket assignment
No dedicated labels or statistic
I1.4 Redmine decommissioning
Global FAE community
RECN
REA REIN REL
REE
TPS_team_MCU
i1.1
i2.1
i1.3
TMAE_team_MCU
i2.3
i2.4 Not clear direct ticket assignment
No dedicated labels or statistic
i5.1, I5.2, i5.3
Temporal support setup (initial phase for new product)
Disti
i1.0
TPS_team_MCU_Tools
i2.2
i2.4
i2.5
Andreas T to provide list of the SWDD, ASDD
Radar
FDT_HWA

## Slide 4
JIRA Global Support Structure (detailed view)

## Slide 5: Discussed structure
A-High Touch
B-Mid Touch
C-Low Touch
D-No Touch
L1 / FAE
L2
L3
REN FAE
REN FAE
Renesas FAE
L2 AGAP team
L2 AE team
Renesas FAE
Disti FAE
21-10-2022
m1
m2
m3
m4
m5

## Slide 6: Customers Support models
A- High Touch
B-Mid Touch
09-11-2022
Model 1
Customer directly opens tickets in JIRA GASG in a dedicated customer portal No disti involved
A- High Touch
B-Mid Touch
Model 3
Disti opens JIRA ticket on behalf of customer in a dedicated customer portal communication b/w customer and Disti not in REN scope;
Customer Portal
Customer Portal
Model 2
Customer directly opens tickets in JIRA GASG in a dedicated customer portal Disti is agent inside JIRA
A- High Touch
B-Mid Touch
Customer Portal
e-mail
Model 4
Disti opens JIRA ticket on behalf of customer in a Disti portal; communication b/w customer and Disti not in REN scope;
C-Low Touch
Disti Portal
e-mail
  JIRA GASG
  JIRA GASG
  JIRA GASG
Disti FAE - Customer
Disti FAE - Customer
D-Low Touch
Model 5
Customer support via web
Renesas.com
Renesas Rulz
Disti FAE - Agent
  JIRA GASG

## Slide 7: Customers Support models
A- High Touch
B-Mid Touch
09-11-2022
Model 1
Customer directly opens tickets in JIRA GASG in a dedicated customer portal No disti involved
A- High Touch
B-Mid Touch
Model 3
Disti opens JIRA ticket on behalf of customer in a dedicated customer portal communication b/w customer and Disti not in REN scope;
Customer Portal
Customer Portal
Model 2
Customer directly opens tickets in JIRA GASG in a dedicated customer portal Disti is agent inside JIRA
A- High Touch
B-Mid Touch
Customer Portal
e-mail
Model 4
Disti opens JIRA ticket on behalf of customer in a Disti portal; communication b/w customer and Disti not in REN scope;
C-Low Touch
Disti Portal
e-mail
  JIRA GASG
  JIRA GASG
  JIRA GASG
Disti FAE - Customer
Disti FAE - Customer
D-Low Touch
Model 5
Customer support via web
Renesas.com
Renesas Rulz
Disti FAE - Agent
  JIRA GASG

## Slide 8: Situation JIRA/OTRS
  Actual situation with “one” label
„TPS_team“
„TPS_team_XYZ“
„TPS_team_SoC“
„TPS_team_MCU“
SoC Team
Member n
Member 1
Member 2
MCU Team
Member n
Member 1
Member 2
XYZ Team
Member n
Member 1
Member 2
„TPS_team“
SoC Team
Member n
Member 1
Member 2
  New situation with “more” teams needs a “hierarchy” with “sublabels”. Existing/old “TPS_team” tickets need to be migrated to new label (“TPS_team_SoC”).
Automated deceision for „sublabels“ based on component:
R-Car
RH850
…
XYZ

## Slide 9
1. SOC issues list
Number | Description
i1.0 | How do we work with Disti in REE and other regions? Who is opening the tickets ? Do we create Project per customer or per Disti?
i1.1 | Need to strengthen alignment: Info sharing, doc distribution
i1.2 | Direct ticket assignment. No dedicated labels or statistic. missing transparency
i1.3 | Work with distributors. Need closer alignment with BPs and check NDAs

## Slide 10
2. MCU issues list
Number | Owner | Description
i2.1 | Antonio | Need to define model for the tickets distribution between FAEs (FAE operation model) Ticket distribution per customer to related FAE Ticket distribution per SME Ticket distribution per Product
i2.2 |  | Missing common ticket tool and Knowledge Base (OTRS and JIRA, Team Support)
i2.3 |  | Need to strengthen alignment: Info sharing, doc distribution
i2.4 |  | How to handle SPAM mails? (OTRS uses a special Queue, so that they are not counted in the statistic)
i2.5 |  | Is JIRA able to create user-defined "reminders"? ( OTRS use various user-defined pending status to support the agent)

## Slide 11
5. General issues list
Number | Description
i5.1 | Missing coordination for the initiative “Global FAE community”
i5.2 | Distributed MCAL support (MCAL support team using JIRAs ASR, GASG and OTRS)
i5.3 | Missing general ticketing tool for all products

## Slide 12
Proposal on the next steps
16.09.2022
Proposal:
Define and initiate project (phases of the project)
Define prio of the scope coverage (ref to the issue list)
Define and agree on the budget of the project, phases of the project
Define working groups for each phase of the project (steering come and working level or 2 in 1)
Define schedule for each phase of the project
Kick off activity (hold kick off meeting)
Communication mng: setup re-occurring meetings and coordination of the activities

## Slide 13
2. MCU

## Slide 14
i2.1 Need to define model for the tickets distribution between FAEs (FAE operation model)
Option 1:
“Groom FAE”
220215 FSE_FAE Customer Responsibility.xlsx
FAE prime
Option 2:
Directly to SME
Registered user
Or generic e-mail address (queue)
FAE deputy
FAE SME
Phone call or not to use personal e-mail?
~
FAE prime
Registered user
Or generic e-mail address (queue)
FAE deputy
FAE SME
Phone call or not to use personal e-mail?
Watchers of the tickets
~

## Slide 15
i2.1 Need to define model for the tickets distribution between FAEs (FAE operation model)
Each case has to cover most comment cases for the customer support (Aprox 990%)
Scalability to consider:
      Customer
      Product
      SME (I-shape or T-shape specialist)
      Region (ree, REA, RECN, REL, REA)

## Slide 16
OTS migration

## Slide 17: OTRS migration – Schedule
17-08-2022
 | July 2022 |  | August 2022 |  |  |  |  | September 2022 |  |  |  | October 2022 |  |  | 
Activity | CW29 | CW30 | CW31 | CW32 | CW33 | CW34 | CW35 | CW36 | CW37 | CW38 | CW39 | CW40 | CW41 | CW42 | CW43
Bosch Unicon Unimind |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
“One for all” Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
?potential JIRA PRD migration from OTRS
Define Support Structure
POC1 for basic requirements:
1. e-mail communication for registered/unregistered users
2. OAuth 2.0
3. Connect few e-mail queues to one JIRA Project
Now
Confluence materials update
  Support over OTRS
    Dedicated support
    Major customers
    On-board to existing customer portals/projects
    Example: Bosch Unimind, Unicon
    General support
    Following customers, potential customers
    “One for all” portal/project
    Example: MCDC support for Renesas Rulz
JIRA DEV deployment
JIRA PRD deployment
JIRA DEV deployment
Demo
Gather new requirements
POC2 for extended requirements:
Migration of the existing tickets
Support Structure
Define Support Structure
~
Notes: カスタムフィールド
・除外：案 - 代替案で対応出来ている
・SDK Type判定：案 - 代替案で対応出来ている、S4よりも後でよい
・ツールチェインかサポートコンパイラの情報：案 ★ - 代替案で対応出来ている
・SPILS - ？(値の追加なので背景が必要)
・SW OS Name に Zephyrを追加：Zephyr対応前に必須 ← OTLINTに紐づいている？
  V4H Zephyr, Vision FWKのチケット作成（やり方はしっている人前提）
    CPUコアの属性の追加が必要。仕様決めが発生する
    5月末に先行リリース（チケットで対応しなくても可）
    6月にトライアル
    7月パッケージリリース
  S4のCONFDB対応をいつにするか（初めての人が多い）
    仕様見直し。Custom fieldの変更が必要。～５月末
    6月にチケット作成
    ターゲット: 6/M or 7/M
チケット追加Trial パッケージ作成本番リリース 1V3H/V3M4/E5/E6/E2Non SDK4/E?5/E?6/E?3ZephyrOSパワポだと5/Mだが→5/Eシフト予定6/E7/E4VisionFWKパワポだと5/Mだが→5/Eシフト予定6/E7/E5S4パワポだと5/Eだが→5/Mシフト予定6/M7/M

## Slide 18
FAE/AE mailing list

## Slide 19
FAE mailing list
TBD

## Slide 20
Distributors on-boarding (RENJRC-3899)
GENDITI_ABU

## Slide 21
Distributors on-boarding – original proposal & questions
      AM & EM
GEO | Distributor | Regional Sales leader | SoC Ticket Receiver | SoC Ticket Watcher | MCU Ticket Receiver | MCU Ticket Watcher | SoC GSS | MCU GSS | Regional FAE mng (added as watcher) | Comment
AMERICAS | AVNET |  | AGAP Jira „TPS_team_SOC“ | Quan Li | AGAP Jira „TPS_team_MCU“ | Hardik Shah | REA_FAE | TPS_team_MCU or TMAE_team_MCU | SoC & MCU Fred Gordon A&P Mark Lissner | REA_FAE Quan Li (REL/US) prime Jeffrey Booker (REA/US) alternative/watcher TPS_team_MCU – no direct tickets assignment
EMEA | AVNET |  | AGAP Jira „TPS_team_SOC“ | N/A | AGAP Jira „TPS_team_MCU“ | N/A | TPS_team_SOC | TPS_team_MCU or TMAE_team_MCU | SoC & MCU Andreas Erlebach A&P Joerg Weeger | 
CHINA | Yuban E-Touch Teampo |  | Jeff Fang | Haijun Chen; Gaowei Li | Lina Chang; Sophia Jiang | Jianfeng Wang; Yi Zhan | RECN_FAE | RECN_FAE? | SOC&MCU : Tao Yu A&P Power : Barney Hu Power management : Barney HU Analog : Jason Lu | Need MCU label for RECN who is in the RECN MCU team? RECN_FAE Asignee: Haijun Chen (REL/CN) Deputy/watcher Gaowei Li (REL/CN) Jing Yan (REL/CN)
JAPAN | Hagiwara Tokai Ryosan Shinko Glosel Ryoden Tachibana Ryosho |  | Kunihiro Tosho Toru Aoyama | - | Takayuki Kaneko Kyoukou Gi | - | REL_FAE REL_SW REL_HW REL_Fusa REL_Tools |  | Tbd.... | Do we need to extend the labels base on the REL FAE support structure?
KOREA | Gentech Leaderstech |  | Tony Cho | Neo Kim Mason Shin Luis Kim | Luis Kim | Mason Shin Neo Kim Tony Cho | REKR_FAE | REKR_FAE? | RECN All:HJ Cho | REKR_FAE Primary: Tony Cho (REKR/KR) Secondary: Neo Kim (REKR/KR) Deputy/Watcher: Seungmin Shin (REKR/KR) Tony Cho (REKR/KR) Neo Kim (REKR/KR)
INDIA | Rabyte Macnica Hagiwara |  | Nagesh Gad | Amit Sharma | Rachit Choudhary Pramod Patil | Nagesh Gad | REIN_FAE | REIN_FAE? | SoC & MCU Srikhanth Nagarajan A&P Vrao Pendyala | REIN_FAE Prime: Ravi Thankaraj (REL/IN) Deputy/Watcher: Mohammed Yaseen (REL/IN)
TAIWAN | Koryo WT Micro |  | Paul Wang | Yasuhiro Yamakoshi Yajun Wu | Paul Wang | N/A | RETW_FAE? |  | Taiwan All Victor Wang | No GSS; need label for RETW_FAE; Who is prime and who is deputy?
APAC OTHERS | Macnica Avnet WT |  | AGAP Jira „TPS_team_SOC“ |  | AGAP Jira „TPS_team_MCU“ |  | TPS_team_SOC | TPS_team_MCU or TMAE_team_MCU | SG/SE Asia : TP Tay | 
18-01-2023

## Slide 22: Issue statements
Issue statements:
Alignment with GSS Proposal for the tickets distribution below is not aligned with Global Support structure - Global Support Structure Labels overview: GSS_labels_overview_v.1.0.xlsx
      AI: Need confirmation: for REE, RECN, REIN, REKR can existing Support structure to be used?
      AI: Need to define Support structure in Taiwan (as part of GSS), for each JIRA component – JIRA “light”
      AI: Need confirmation: Do we involve REN FAE in to communication model ?
      AI: what is the support structure for MCU in other regions ? As of now for MCU tickets are re-direct to the same FAE in the regions
      AI: need to define support structure in the REL; REL has broader FAE team and also usage of other tools (complex issue)
      AI: should GENDISTI work in similar was GENBP; first assingemnet to be done to QA person; Who will be controlling Disit from REN side?
Work with Distributors
      Proposal to setup General Distributors Portal (GENDISTI) it will work for all regions except of REL;
      Base on the models which are presented (sl 22) REL distributors already working base on Model 2; it means if they will get access to GENDISTI, then they will be able to see complete project as they work as JIRA Agents; Can this be covered by NDA ?

## Slide 23: Next steps
Proposal from JIRA Admin Team
Clarify AI listed in previous slide
Create GENDISTI portal (to be used for all regions except of REL)
  Each Disti will see ticket only from it’s own organization, but for all customer with which this Disti is working
Define support structure in REL

## Slide 24: Customers Support models for high touch customers
A- High Touch
B-Mid Touch
09-11-2022
Model 1
Customer directly opens tickets in a dedicated customer portal No disti involved
(Customer or product based)
A- High Touch
B-Mid Touch
Model 3
Disti opens JIRA ticket on behalf of customer in a dedicated customer portal communication b/w customer and Disti not in REN scope;
Customer Portal
Customer Portal
Model 2
Customer directly opens tickets in a dedicated customer portal Disti is agent inside JIRA
A- High Touch
B-Mid Touch
Customer Portal
  JIRA GASG
  JIRA GASG
Disti FAE - Customer
Disti FAE - Agent
  JIRA GASG

## Slide 25: Customers Support models for low touch customers
09-11-2022
Model 6 (under development)
Customer send e-mail, tickets opens automatically in JIRA GASG in a free for all customer project No disti involved
e-mail communication
  JIRA GASG
D-Low Touch
Model 4
Disti opens JIRA ticket on behalf of customer in a Disti portal; communication b/w customer and Disti not in REN scope;
C-Low Touch
Customer Portal
e-mail
  JIRA GASG
Disti FAE - Customer
D-Low Touch
Model 5
Customer support via web
Renesas.com
Renesas Rulz

## Slide 26: Customers Support models for high/low touch customers
09-11-2022
Vertical / Regional
High Touch/Low Touch
JIRA GASG
Model 7
FAE or Online AE enters JIRA ticket on Agent side.
BU AE team are 1st responders
#1 case – majority

## Slide 27: Avnet silica Project Structure (for R-Car) – Europe (RENJRC-3780)
Avnet Silica's Customer
Avnet Silica Local FAEs
REE ABU TPS team (Frank)
Level 1
ABU ADMKD (Anne)
Level 2
ABU (HW/SW development)
Level 3
Coordination between Actia and Renesas’s teams
AI Follow Up & Ope issue tracking
Set up & drive regular Projet meeting with customers
Escalatont rigger
Avnet Silica Sales
ABU ADMKD
(Marie-Claire, Eric)
Marketing,
Facilitator
Avnet Silica “R-Car FAEs”
Jira
REE ABU
(Wido)
Sales
      Marie-Claire Proposal

## Slide 28: notes
For each project at distributor’s customer we will create a sub-project on the distributor’s Jira portal. Many small customers in this case. Several distributors – lead are 2 (EBV, Avnet Silica), others later.
Distribution customer has no access to Jira. Open: has Avnet Silica experience with Jira?
Products: R-Car Gen3e, V3x
  New for Europe but existing distribution support model in other regions (Korea, Japan etc) in similar way. Consistency (across regions) to be considered.
  What about single Jira distribution customers' portal; then sub-project per customer -> distributor's name_customer's name. See queues associate to each customer -> can sort by distributor. This is simpler to handle/maintain from Jira management point of view.
  No NDA between distributor's customers and Renesas => avoid direct support
  Next step: Elvira to check setup in other regions

## Slide 29
Additional slides

## Slide 30
REN Tools and products overview

## Slide 31
Tools and products overview
Sources
Requirement Engineering PJ_Rollout_Phase1_charter.pptx
220215 FSE_FAE Customer Responsibility.xlsx

## Slide 32
Renesas.com