## ref
Milestone
Updated by
25.01.13
Opp | No. | Issue title | Issue detail | Progress | Update | A/I | PIC | Due date | Remark
FCM (POC) | 1 | Workshop (CW03~CW13) | By Teams meeting, Training for HKMC | Open | #1/10, 협의 - 1월말, BOM 기준 비교 검토 - 2월초, POC 최종 선정 | Follow up Workshop agenda | Tony | CW13 | #1. PL은 Roy, Tony는 Workshop 지원만 대응
이슈에 대한 주요 키워드로 제목 입력
이슈 상세, 기술적 상세 내용 기술
상태
Open or
Closed
해당 이슈 관련 Update 정보 기술
Action Item 상세 기술
그외 주요 정보 또는 상황 기술
Schedule
SOP
Dev start
DV
PV
NOW
D-IN
Opp name

## HKMC_FCM
Milestone
Updated by |  |  | Plan: 12월 평가, 데모 / 26년 RFQ 예정 | V4H EVB 1대
25.01.13 |  |  | 현재 V4H로 진행, 상반기 인식 스텍 포팅, 2H는 최적화 작업(V4M과 비교 선정)
Opp | No. | Issue title | Issue detail | Status | Update | A/I | PIC | Due date | Remark
FCM (POC) PL: Roy | 1 | Workshop (CW03~CW13) | By Teams meeting, Training for HKMC | in progress | #1/10, 협의 - 1월말, BOM 기준 비교 검토 - 2월초, POC 최종 선정 | Follow up Workshop agenda | Tony | CW13 | #1. PL은 Roy, Tony는 Workshop 지원만 대응
| 2 | EVB Purchase | Whitehawk(V4H) or Grayhawk(V4M) | in progress | Customer plans to buy 3 or more units. - We need to prepare 6 units as a basic plan. - HKMC is also considering changing the model to V4H. - Not yet clear whether to purchase Whitehawk or Grayhawk. | Check inventory for Whitehawk and Grayhawk. | Roy |  | HKMC 는 이 부분에 대해 영업팀과 논의중 | - 보드 구매는 자동차가 지불 -
| 3 | CAM Bringup done
|  | CAM tunning 작업 - SMA 예정 | Bruce 이사 Pushing
Schedule
SOP
Dev start
DV
PV
NOW
D-IN

## 42dot
Milestone
Updated by
25.01.13
Opp | No. | Issue title | Issue detail | Status | Update | A/I | PIC | Due date | Remark
HPVC(POC) | 1
Schedule
SOP
Dev start
DV
PV
NOW
D-IN

## MOBIS_PRK3
Updated by
2025-02-06 |  |  | Weekly: Regular OPL | 자산관리.xlsx
Opp | No. | Type | Issue title | Issue detail | Status | Update/Result | A/I | PIC | Raised | Due date | Remark
PRK3 PL: Tony MCU: Luis PMIC: CM |  | SoC | DSI1 output on Linux | DSI1 output on Linux | Done |  | DSI1 output validation | Roy | 2024-12-20 | 2025-01-24 | [REKR_MOBIS-422] [REKR_MOBIS][SW][V4H] How to enable DSI1 on Whitehawk - Renesas OneFieldJIRA
|  | SoC | CSI-TX evalution on Logging device | Dual CSI-TX output evaluation |  |  | CSI-TX 측정 환경 setup | Tony | 2025-03-31 |  | [REKR_MOBIS-428] [REKR_MOBIS][SW][V4H]CSI-TX on Linux - Renesas OneFieldJIRA
|  | SoC | CSI-TX on QNX | CSI-TX on QNX | Done |  |  |  | 2025-01-03 | 2025-01-24 | [REKR_MOBIS-427] [REKR_MOBIS][SW][V4H]QNX CSI-TX driver request - Renesas OneFieldJIRA
| High | SoC | GPU init failure | GPU init failure & SW patch | Done | REKR_MOBIS-423_AI.xlsx | (1) SWAP test: 5EA (2) LSI reball to REL: 2EA(Done) (3) V4H EVB <> 2nd board swap(Done) | Tony | 2024-12-23 |  | [REKR_MOBIS-423] [REKR_MOBIS][SW][V4H]GPU driver initialization error - Renesas OneFieldJIRA
|  | SoC | CEVA DSP debug guide | CEVA DSP debug guide | Done |  |  | Jaime Aranguren | 2024-11-04 |  | [REKR_MOBIS-377] [REKR_MOBIS][SW][V4H]CEVA DSP debug on HW board - Renesas OneFieldJIRA
|  |  | V4H-5 SDK Plan | V4H-5 SDK Plan | Done | V4H-5 v3.1 schedule fixed by E/O Apr( 3.37 ) |  | Tony | 2025-01-27 |  | From SDK 3.36.0 to SDK 3.37.0, it can support V4H-5 v3.1 SoC.
|  | SoC | V4H v3.1 FCPR bug | CPM requested to check FCPR use case | Done | FCPR 사용하지 않음 | 현재 사용하지 않음 | Tony | 2025-02-04 | 2025-02-14
|  | SoC | Arranging online meeting |  | Done |  |  | Onoriu | 2024-12-15 | 2025-02-06 | [REKR_MOBIS-418] [REKR_MOBIS][SW][V4H]additional question on: request on sample code of running CVe/CDSP/IMR on multi threads or multi process - Renesas OneFieldJIRA
|  | PMIC | PMIC, Buck Controller, SPS by Jun'25 | CS sample delivery for proto event | Progress |  |  | CM
| P1 | MCU | CR52 - Hang up issue by MPU Configuration | CR52 - Hang up issue by MPU Configuration | Done | 부팅 순서에 따라 증상이 완화되었으나, 간헐적으로 OS가 멈추는 증상이 나옴 |  | Luis | 2024-12-12 |  | https://onefieldjira.renesas.com/browse/REKR_MOBIS-443 https://onefieldjira.renesas.com/browse/REKR_MOBIS-432
|  | MCU | MCAL - GPT Configuration | MCAL - GPT Configuration | Progress |  |  | Luis | 2025-01-17
|  | MCU | MCAL - SPI Multi core usase | MCAL - SPI Multi core usase in interrupt point of view | Done |  |  | Luis | 2025-01-24 |  | https://onefieldjira.renesas.com/browse/REKR_MOBIS-458
| P1 | MCU | MCAL - SPI CLK 10MHz Configuraiton | MCAL - SPI CLK 10MHz Configuraiton | Done | MSO를 80MHz로 설정하고, SPI_DIV와 BAUD_CFG를 각각 4, 2로 설정할 경우, SPI CLK는 10MHz 가능, 검토예정 |  | Luis | 2025-01-24
|  | MCU | MCAL - SPI DMA and CACHE's relevance | MCAL - SPI DMA and CACHE's relevance | Progress |  |  | Luis | 2025-01-24 |  | https://onefieldjira.renesas.com/browse/REKR_MOBIS-517
| P1 | MCU | MCAL - SPI CS configuration | MCAL - SPI CS configuration | Done | GPIO로 CS 할당할 경우 동작 가능성 확인 예정 |  | Luis | 2025-01-24
|  | MCU | MCAL - CDDIIC Build error | MCAL - CDDIIC Build error | Progress |  |  | Luis | 2025-01-24
|  | MCU | MCAL - GPT ISR CAT2 configuration | MCAL - GPT ISR CAT2 configuration | Progress |  |  | Luis | 2025-01-17 |  | https://onefieldjira.renesas.com/browse/REKR_MOBIS-448
|  | MCU | MCAL - ICCOM Configuration | MCAL - ICCOM Configuration | Progress |  |  | Luis | 2025-01-24
| HIgh | PMIC | RAA271005 buck1 short | Buck1 short occurred when try first booting after highloader image download and CA-76 core 4ea enabled | Done | 3차보드 검토중 | Remote sense setup sees larger spikes of voltage and it looks like noise introduced into fb line causing disturbances into the control loop. BU recommended R423 and R424 populated in order to solve spike voltage. | CM | 2025-01-24
|  | SoC | SWAP EVB 동작 확인 |  | Done |  |  | Tony
|  | SoC | SWAP PRk3 개발 환경 setup |  | Done |  |  | Tony
|  | SoC | PRK3 - 2nd board 개발 환경 setup |  | Done |  |  | Tony
|  | SoC | JIRA-451 | EVB와 PRK3 보드가 정상동작인지 확인 필요 | Closed |  | 플랫폼팀 담당자 미팅 진행 | Tony
|  | SoC | Stanley 미팅 | Stanley와 미팅 예약 | Done | Camera framework discuss | 차주 화요일 Full로 미팅 | Tony
|  | SoC | DVFS는 지원여부 |  | Done | DVFS 미지원/Voltage 변경 지원 |  | CM | 2025-02-07 | 2025-02-09
|  | SoC | OPTEE&SMONI - BL31 package relase |  |  | SMA로 relase block |  | Tony |  |  | https://onefieldjira.renesas.com/browse/REKR_MOBIS-446
|  | SoC | BSP에서 GPIO로 변경을 진행 | 관련 pin 확인 필요 | Done
|  | SoC | HW revision history |  | Done |  |  | UQ-Ken
|  | SoC | MX66U1G45GXDQ00) ECC correction | ECC correction을 위한 별도의 pin이 존재여부 | Done |  |  | UQ-Ken |  |  | [REKR_MOBIS-438] [REKR_MOBIS][HW][V4H]Nor Flash memory Support (Macronix, 1Gbit) - Renesas OneFieldJIRA
|  | SoC | Un-used CS1 pin in memory | Mail: V4H-삼성 LP5 호환 문의 건 | Done |  |  | UQ-Ken |  |  | https://onefieldjira.renesas.com/browse/REKR_MOBIS-449
|  | PMIC | DCIR simulation | voltage drop 관련 simulation | Progress |  |  | CM | 2025-02-17
|  | PMIC | Jesus warp up meeting A/I |  | Done |  |  | CM | 2025-02-14 | 2025-02-28
|  | SoC | 카메라 해상도: 1824x1536 |  |  |  |  | Tony | 2025-02-27
|  | SoC | RVAS Display 출력 |  | Done | Non-resetting SER IC |  | Tony
|  | SoC | OPTEE delivery delay |  | Done | OPTEE official release done |  | Tony
|  | SoC | ISP timtout 이슈 지원 |  | Done | Deepankar와 협력, 50회 테스트 이상무 |  | Tony
|  | SoC | V4H-3 Highloader app 18W on Linux | EVB 재현 가능 | Progress
|  | SoC | FuSa integration |  | Progress
|  | SoC | FMEDA FIT Result |  | Progress |  |  | Tony | 2025-03-25
|  | SoC | Cam init 초기화 Broadcasting |  | Progress |  | (0x80) 8bit I2C write support | Tony
|  | SoC | VSFW 2nd drop update |  | Progress |  |  | Tony
|  | SoC | Renesas coding ruleset report |  | Progress |  |  | Tony | 2025-02-03 | 2025-04-01
|  | SoC | FESCARO HSM(ICUMXB) FW code 지원 |  | Progress |  |  | Tony
|  | SoC | IPL V4H-7 -> V4H-5 지원 |  | Progress |  |  | Tony
|  | MCU | MCAL - SPI CS Delay reduction |  | Progress |  |  | Luis | 2025-03-11 |  | https://onefieldjira.renesas.com/browse/REKR_MOBIS-508
|  | MCU | MCAL - PLL Re-setup by MCU Module |  | Progress |  |  | Luis | 2025-02-23 |  | https://onefieldjira.renesas.com/browse/REKR_MOBIS-487

## MOBIS_Gen5
Milestone
Updated by
25.01.13
Opp | No. | Issue title | Issue detail | Status | Update | A/I | PIC | Due date | Remark
Gen5 POC | 1
Schedule
SOP
Dev start
DV
PV
NOW
D-IN

## HKL_ADCU
Milestone
Updated by
25.04.28
Opp | No. | Issue title | Issue detail | Status | Update | A/I | PIC | Due date | Remark
ADCU-50 | 1 | MCAL development with gnu arm compiler | check the feasibility of that gnu arm compiler can be used for the MCAL development | Done | SIU provided the build configuration of MCAL using gnu free compiler and HKL responded to build and test it successfully |  | CS Park | 2025-02-28 | SOC-1066
| 1 | External Flash writing tool (Gang tool) | HKL need something to be able to burn the images on the ADCU-50 system for purposes of maintenance and upgrade. | Hold | HKL is preparing flash burning equipments for mass-production; making filesystems to burn flashes is missing in the burning equipment | check the feasibility to read and save flash data. | HKL | 2025-04-11
| 3 | Car tool and Fusa workshop | as HKL requested how to get the FMEDA infos for R-Car, Car tool and fusa workshop were preparing | Done | V4M R-Car FMEDA library file has been delivered |  | CS Park | 2025-03-21
| 2 | CV(Concept Validation) Test Application (Jun~Jul planned) | HKL need a CV test app for testing the SOC's reliability and durability | In Progress | Joe and Stanley shared the result which is a linux version of load generation tool and working on porting works from Linux version to Qnx version | check the ETA of Qnx version of the tool | Joe W (Stanley) | 2025-04-30 | SOC-1120
| 5 | Board bring up support by BU | HKL asked to support a board bring-up from March 17th. A request to dispatch a BU engineer accordingly is discussing. | Done | The Board bring-up support has been successfully done by manipluating flash writer, IPLs and uboot with NXP phy ICs. |  | CS Park, Adam Bass | 2025-03-14
| 6 | Thermal Test Specification | BU shared that V4M samples before CV event must not be tested in thermal test because it goes failures; need to check the CV test schedule and thermal test spec | Done | the thermal test spec is required for HT(High temp) samples, so let genie know it and coordinate the sample deliveries accordingly; HKL requested us all samples should be provided over HT samples except for 20EA for the 1st sample board |  | CS Park | 2025-02-26
| 3 | purchase and loan of arm safety compiler | HKL requested us to provide free compiler license of Autosar/MCAL development as same as TI did. | Done | licenses have been done to deliver and setup at HKL. |  | CS Park | 2025-04-11
| 4 | Request to release HSM image | I noticed I should request an HSM image runing on ICUMX core. it will be used for OTA and Diagnostic early in the project. | Done | [04/10, Youmi] Delivered ICUMX FW download link and security guide document download link [04.04, Ralf] Dear Ishiguro-san, We got a request from HL Klemove to open ICUMX related information as available on the following secure portal https://www.renesas.com/en/secure/r-car-v4msec-secure-content How can we make this available to the customer? [03/21, howard] Yamazaki san is still working on the 1 click ELA for the Gen4 Security SW. I've asked him for a update and put you on copy, once we get his feedback we can see how to proceed. | Deploy ICUMX guide and ICUMX FW | Stephane | 2025-04-11 | SOC-1192
| 9 | build environment setup for board bring up | HKL hasn't assigned anyone to support BSP portion at the 1st board bring up | Done | All IPL build setup and uboot build setup have been installed at either laptop or ubuntu server. | three different IPL build environments setup from REKR side | CS Park | 2025-03-16
| 10 | EB Autosar schedule | HKL asked to pull in EB Autosar schedule especially the 1st dev drop before March '25 as well as the ASIL D RFM release before March '26 | Done |  |  | Mason | 2025-03-03
|  | New IC components check | HKL requested us to check new LPDDR5 ICs and eMMC ICs whether they are supported on V4M or not | Done | LPDDR5 MT62F2G32D4DS-023(8GB) / x2ch, x2rank -> Supported MT62F4G32D8DV-023(16GB) / x2ch, x2rank eMMC SDINBDG4-32G-ZA(32GB) -> Supported SDINBDG4-64G-ZA(64GB) -> Supported | check the ICs can be supported by V4M | CS Park | 2025-03-31 | SOC-1418
| 5 | MCAL session | HKL requested us to provide a MCAL training session for a new members who are assigned | Done | REN KR delivered a MCAL training session to new assigned members taken in charge of Autosar at HL Klemove on April 1st. |  | Luis Kim | April 1st
|  | IPL hands-on session | HKL BSP engineer has been assigned very late since Renesas kept asking from Feb. need to transfer what we did during the board bring-up support in order of him to support other bring-up by himself. | Done | IPL hands-on session has been successfully done to convey all manipulations that we fixed in the IPLs and uboot. | deliver a IPL hands-on session (March 25th) | CS Park | 2025-03-30
| 6 | 2nd sample board bring-up | HKL requested us to be ready for the bring-up at Tuesday, April 8th to assist the bring-up of an ethernet switch IC on uboot | In Progress | There is no issue during the 2nd board bringup. the ethernet configuration of QNX had a problem and was reported and resolved by HKL's platform SW1 team. | check the u-boot codes and release it to PG | CS Park | April 11th
| 7 | Security Training session | HKL requested us to provide a security session of V4M | Done | Asari-san provided the first session of the training for HKL moderating by CS and he asked REN KR to check HKL's questions to prepare and cover them at the second session | Check HKL's questions about the R-Car security | Youmi, CS Park | May 14th
|  | OTA feasibility check with CM version of V4M | HKL requested us to check how to implement his OTA feature with CM version of V4M | Not Started | CM version of V4M doesn't support secure boot, however, it needs to check secure flash with it. | request this to Kevan, Product FAE | Kevan | April 30th
|  | Booting failure issue | HKL reported to us that ADCU-50 board sometimes gets a symptom of booting failure and requested us to analyze it | Done | the issue caused | prepare the plan to support | WS Lee, CS Park | April 30th
|  | Cx 2nd IPL issue | Autosar spec needs to sync all CR cores to start Autosar OS but Cx 2nd IPL occupied CR1 core after the OS is starting | In Progress | A meeting with EB Korea concluded that EB Safety Autosar OS (ASIL D) also requires synchronizing all CR cores before starting the OS. | meet HKL to discuss this issue and check other options | Luis, CS Park | April 30th
|  | HKMC Secure coding compliance | HKL request us to comply with HKMC secure coding rules for Renesas softwares (SDK, MCAL etc) | In Progress | HKMC has been forcing on that all his suppliers comply with his secure coding rules. | keep checking the statuses | CS Park | Oct 31th | SOC-1499, SOC-1500
|  | Rox Platform Demonstration | following up Cyril's visit to HKL, Rox Platform Demo is one of the action items | Started | asked Stanley Liu to coordinate someone to support the demo and got the image files of the demo | review the images and check the availability of a V4H whitehawk board | CS Park

## HKL_APCU
Milestone
Updated by
25.04.28
Opp | No. | Issue title | Issue detail | Status | Update | A/I | PIC | Due date | Remark
APCU-10A |  | OPTEE support plan | OPTEE support plan for HKL and V4M | Done | Wait for response from Karthik/Dongwen [02/21] OPTEE support plan have been deploy to HKL | Deploy to HKL SW team leader (namgyu.oh) | Michael Klein | 2025-02-05 | SOC-1172
|  | QNX SDP8.0 support plan | SDP8.0 is needed to meet HKMC secure coding rule | holding until customer request SDP8 officially | [02/28, Youmi] HKL will start development with SDP7.1 first, and QNX will support SDP8 upgrade if HKL decides to upgrade to SDP8 by November this year. If HKL does not decide whether to upgrade by November, the upgrade clause for SDP8 will be ineffective. [02/19] After checking about this with QNX Korea today, QNX FAE said that they haven't received the request for SD8 BSP officially from HKL yet. [02/13] HKL must officially request SDP8.1 from QNX to proceed with the process [02/06] Synch w/ Howard: Responsible for schedule: Dongwen Typically internal budget for dev. Provide to QNX, sells to customer Important: Porting effort between xOS and BSP -> no experience how long it would take | Deploy to HL Klemove and QNX (yonlee) | Michael Klein/Howard Williams | 2025-02-06 | SOC-1171
|  | V4M durability and reliability data | SoC stability data in high load situations | Done | Data on V4M will be provided later, and first, data on V4H-7 v2.2 were obtained. | Deploy to HKL HW team leader | Michael Klein | 2025-02-03 | SOC-1065
|  | Video logging, M2M conversion tool | Provides tools for ISP tuning and AI recognition | In Progress | [04/02, youmi] Discussions are underway between Ryan Stanley and Bjoern Toschi regarding M2M conversion tool support. [04/02, youmi] As the base OS of the camera app for ISP tuning is changed to QNX in SOC-1413. Please support the M2M conversion tool based on EVB/QNX as well. HKL wants to integrate the development environment on QNX. [03/05, youmi] according BU guide, I explained that the PC I/F, and PC program are the area that the customer has to do. [02/24, youmi] It is true that HKL has an application source code (python) on the PC side, but since there is no source code on the board side, it is difficult to figure out what protocol works between the two apps, so it seems difficult to reuse that code. HKL wants to get an example that includes the entire execution process. If the bin (raw image) part is difficult, HKL expects Renas to provide the part that processes at least one raw image. Please consider this part and review it again. [02/19, stanley] Based on the discussion with HKL during KO, my understanding is that HKL can reuse the application code they have on TI platform for input/output interfacing with PC tool. The Protocol part between PC and SoC is HKL specific implementation. Ethernet part is OS specific so it is common. Providing ISP m2m example should be sufficient from Renesas side. [01/30,Anne] Anne team f/up m2m part. Anne request Stanley to take over the transmission (input/output) part [01/23] Discussions are underway between BU and MMS based on customer requirements. | Deploy to HKL (younghun.choi) | Bjoern Toschi/ Youmi | 2025-04-30 | SOC-1061
|  | Build environment constraints when using Matlab Simulink-based code | HKL SVM team use Matlab Simulink for SVM development. Please let me know build environment constraints when using Matlab Simulink-based code. | Done | [03/13, Youmi] As the customer registers the SOC-1366 Ticket, this ticket will be closed. [03/07, Ralf] Customer requirements need to be more clarified [03/05, Youmi] Please see Jaime's answer and assign the person in charge to ETVPF_R-Car_V1.00 so that V4M can also be supported. If potting takes time, please help to start the work in advance. [03/04, Jaime] It is for me clear that developing and validating algorithms from Simulink targeting the RT-Core in V4x (CR52) is possible today. Also, if the restriction to the listed blocks is acceptable, it can also be fully simulated and validated in virtual environment (including GPIO, CAN and Ethernet communications), assuming that (virtual) V4H is acceptable for such development and validation. Now, for specific V4M support, I think more investigation and adaptation will be needed. An additional comment: in any case, if the customer is not interested in the validation within a virtual model, or is also not interested on any of the supported peripherals, and is only interested in getting the code generated by their Simulink model running on the CR52, they can freely proceed without the Embedded Target for R-Car Virtual Platform, and simply use Mathworks Embedded Coder (+ Simulink Coder + MATLAB Coder) to generate C/C++ code from their model and in their IDE / toolchain of preference import that code, build it, run it, debug it, profile it, etc... [03/04, Youmi] Parking app is implemented by fusion of image recognition data handed over by AI and the results of ultrasonic sensors. And Parking app operates on AutoSar/MCAL/RT-Core and is developed using Matlab simulink. Development will proceed with simulink 2024a, and mass production will proceed with simulink 2018b. Please check if simulink is supported in RT-Core in V4M. [Embedded Target for R-Car Virtual Platform V1.00.00 ¦ Renesas¦https://www.renesas.com/en/document/swo/embedded-target-r-car-virtual-platform-v10000] [02/24, Jaime] It is not clear what exactly is HL Klemove pretending to do here. Automatic code generation from Simulink or MATLAB? Although MATLAB and Simulink have code generators, there are no code generators that are customized (data types, memory layout, vectorization) for SP500, even less that are integrated for usage on our SoC. Of course, the customer is free to use the code generators of MATLAB/Simulink to generate generic C/C++ code for their algorithm, but they have to manually adapt it to build with the existing toolset (CEVA SensePro), and most importantly, understand it if they see the need to optimize it (mostly they will). Of course, there exist also the so called "embedded coder" for MATLAB/Simulink, but that is nothing else than the generated code taking care of some standard data types (8, 16, 32 bit, according to the selected processor architecture). But there is nothing that takes care of e.g. vectors. Please indicate with a bit more detail what the customer is pretending to do, maybe we can discuss further, I can also offer having a session to listen to their need and discuss what could be done. But, be very clear upfront that there is nothing like "click this icon in in MATLAB/Simulink and you get highly optimized, vectorized code that runs off-the-shelf in the DSP inside our SoC taking the best in terms of performance and efficiency". [02/24,Youmi] Could you please check whether Gen4 itself is not supporting Matlab/Simulink or only HWA part? [02/21,Onoriu] For xos3 we do not support any automatic generation of HWA code from Matlab/Simulink code. | Provide build environment constraints when using Matlab Simulink-based code. | Onoriu/Jaime | 2025-03-28 | SOC-1201
|  | Simulink configuration for MBD | It's a question of which one should I choose for 'Device vendor' and 'Device type'. It's a question of which one should I choose for Toolchain in Build process. | Done | [03/13, Ralf] Beside Jaime Aranguren (REL/DE), I did not get information about anybody with Simulink experience. From that perspective it is good to know that the MCU FAE team seems to have some experience with Simulink. I would agree their statement regarding core selection. MCAL will run on R52 core, so Coretex-R should be selected. Regarding tool chain to configure, it will be good to contact EB as MCAL integrator. Even though our MCAL delivery describes the requirement on the tool chain (ARM Compiler 6.16.1 tool chain) and the sample applicaitons will also define the tested build settings, I wonder if the integrator will introduce changes. So, they should define the Simulink build settings. My understanding was that a complete and verified configuration for V4M is required. That is the reason why I asked Michael for CPM suppport. If only related to your two questions (Device Type and Tool Chain), I hope that with the answers his support will not be required. | Deliver simulink configuration for MBD | Ralf / Michael |  | SOC-1366
|  | X1D sensor bring-up | Camera sensor bring-up for ISP tuning on EVB | Done | [02/03] It was confirmed that CS works well in EVB. [01/29] isp_rvas_mono_v4m.7z was delivered by Ueno-san. | Deploy camera sensor bring-up code to HKL | CS / Hirotaka Ueno-san | 2025-01-31 | SOC-1035
|  | Preferred vendor lists of eMMC and Flash memory | HW team requests | Done | [02/27, Gotthard] Renesas has no supported/non-supported device list and it will also not been provided to customer- (even not if they push for it). The reference is what is used on the evaluation board. For V4M what is used on grey hawk board. If HLK want to know if some specific device is compatible with V4M they can ask for a specific flash/emmc device type. Then we can check this device and provide feedback to this device. Please close this ticket and open a new ticket if Renesas should check a specific flash/eMMC device type. OTLINT-16148 is in progress | Deploy th HKL (jinhwan.jeong) | Youmi |  | SOC-1063
|  | Setup kick-off meeting | Held kick-off meeting with HKL | Done | discussed the agenda through an internal meeting | Schedule and presenter confirmation required | Michael Klein / Stanley Liu | 2025-02-07 | kick-off : 2/13
|  | Setup HyCo overview on-line session | Setup schedule of on-line session | Done | [02/21] 02/26 2~4PM | Invite on-line session | Yajun-san | 2025-02-21
|  | Setup DSP/CVe overview on-line session | Setup schedule of on-line session | Done | [02/28] 03/05 4~6PM | Invite on-line session | Jaime/Onoriu | 2025-02-28
|  | ISP tuning partner | BU wanted us to check who is the ISP tuning partner; some of ISP companies are rejected to share ISP data by dream chip for instance nextchip | Done | HKL is considering three ISP candidates, MMS, Cogent, and Brycen. no issue with dreamchip | check his ISP tuning partner whether it matters to dreamchip or not | CS Park | 2025-03-14
|  | 1st board bring-up | Need to support by BU [Plan B] Need to support by PFAE | Done | [04/16, Youmi] IPL and uboot (PHY1) bring-up is done. [04/14, Sungmo] Scheduled to arrive at the board around 3-4 p.m. [04/10, Stanley] MS Teams chat have created for supporting APCU-10A bring-up. [04/08, Youmi] PMIC FAE will be on standby in the afternoon of April 15 [04/07, Youmi] Bring-up schedule 4/10 : SMT 4/14 ~ 15 : HKL HW team - check PMIC and signal (target: SCIF prompt) 4/16~ : Renesas IPL and uboot bring-up PFAE Kevan will come to Korea on a business trip from 4/16 to 18 and debug together. [04/03. Youmi] The uboot base code for APCU-10A was written. The octal spidts configuration and the ethernet phy-related configuration require PG assistance. [03/07, Youmi] Stanley teams' plan is shared to Michael and Waiting respond. [03/06, Stanley] Stanley said that board bring-up only supports ADCU-50. For APCU-10A, I received a guide through Michael to discuss with Naoki Yamamoto-san | 1st board bring-up | Youmi/ Kevan/ PG |  | SOC-1273
|  | VSFWK deployment schedule & meeting | Setup VSFWK deployment schedule & meeting | Done | [03/13, Youmi] Stanley explained to the customer directly about VSFKW and the deployment schedule. | Deliver VSFWK schedule & drop1 | Youmi / Stanley Liu
|  | VIN (Video Input) Path online session | Setup VIN (Video Input) Path online session | Done | [03/17, Youmi] Video Input Path on-line session is planed to held on 3/20 5:00~6:00 PM. (Presenter : Wassim) | Send invite for online session | Youmi
|  | EVB board usage guide and X1D mono camera app guide hands-on session for ISP team | EVB board usage guide and X1D mono camera app guide for ISP team | Done | [03/20] Hands-on session held on 03/20 with Uniquest and ISP team. | hands-on session | Youmi/Ken
|  | IMR use case proposal and Q&A session | Setup IMR use case proposal and Q&A session | Done | [03/26, Youmi] IMR use case proposal and Q&A session is planed to held on 3/31 4:00~5:00 PM. | Send invite for online session | Youmi
|  | Security online session | Setup Security online session | Done | [03/28, Youmi] Security on-line session is planed to held on 4/16, 4/23, 5/7, 5/14 4:30~5:30 PM. (Presenter : Shinsuke Asari-san) | Send invite for online session | Youmi
|  | Request for camera App & capture function | 4 camea input & output(4 camera view , selected one camera full) Raw,bmp capture (before/after of ISP) funtion And currently, it is being carried out based on Linux OS for speed, but after the above modifications, I would like to develop on QNX OS and move to above things. | In Progress | [04/04, Youmi] As a result of sync-up with Stanley Liu, the E2E ref app using Linux-based one camera will be distributed by the end of April, and it will be distributed based on QNX by mid-May. The Stanley TF team is working on the support for the four cameras, but some schedule delays are expected. [04/03, Youmi] ISP tuning company decision was supposed to be completed at the end of March, but it is being delayed due to internal situation of HKL. There will be no problem with end of April distribution due to delayed company selection. However, if company selection is completed before the end of April, version distribution may be needed in the middle. This part was agreed by Stanley Liu at HKL sync-up internal meeting today. [04/02, Youmi] We are preparing the QNX based RAW/BMP dump function based on one camera for the end of April distribution. We are also preparing 4 cameras together, but I would also like to inform you that this part may need a little more time. [04/01. Younghun (HKL)] We plan to start ISP development in April. Can you please keep the current distributed Linux version to 1 camera output and just add RAW dump feature(For starting) by this week. Please support 4 camera output and dump (RAW, BMP) function [03/29, Ryan Stanley] Sure, something could be added for this easily. I was doing this already for testing purposes but nothing checked in. We can add something proper. [03/28, Stanley Liu] With your capture node on VSFW, I assume we can dump the ISP output buffer to file in the application? Can you confirm? | Provide multicamera app with raw dump | Youmi |  | SOC-1413
|  | Request sample application to start SVM development | Please give us your opinion on which one we should recommend. Multi camera sample app using RVAS ( SOC-1413 : requested by ISP team ) E2E application based on VSFWK | In Progress | [04/04, Youmi] E2E ref app will be distributed based on QNX by mid-May. The Stanley TF team is working on the support for the four cameras, but some schedule delays are expected. [03/28, Stanley Liu] I suggest SVM team can start with the End of April Engineering drop to build their application. | Provide SVM Sample app | Youmi |  | SOC-1461
|  | gray screen when no input from camera detected | Display gray screen when no input from camera detected OTLINT-16067 : display gray screen OTLINT-16068 : detect missing camera input | In Progress | [1/23, Anne] As discussed (for filing) If the camera stream is interrupted, the system needs to re-initialize again and grey screen shall be shown yes, we know that there are 4 cameras AFAIK What is a better counterproposal here? Let's collect questions and potential counterproposals. [1/21, Wassim] I have some questions regarding this request: What is the purpose of plug/unplug the camera during operations? how the ISP will know about unplugged camera? is there any expected number of cameras in beforehand? why should the ISP output (150,150,150) values, what is the purpose? (please also consider POWER/Bandwidth/ISP_timing/CPU scheduling overhead) | Provide exception handing for detectin no camera | Wassim/ Youmi |  | SOC-1041
|  | API for color format conversion with CVe | action item for IMR use case online session: API for color format conversion with CVe | Done | [04/22, Minchael] Please close this ticket. [04/07, Onoriu] I would like to release an updated version of the V4M project: cve_image_format_conversion_07.04.2025.zip Updates: 1. Supported format conversions (8 bit per pixel for any of them): yuv420sp_to_rgb888p yuv422sp_to_rgb888p rgb888p_to_yuv420sp yuv420sp_to_yuv422sp yuv422sp_to_yuv420sp 2. For each format, several resolutions are supported, the example contains 224x224, 512x320, 640x640x, 1280x944. But you can also easily try different resolutions. See cve_processed_width and cve_processed_widths_per_width computation in r_cve_ifc.cpp. 3. I added run time measurement on top of the VSFWK API on ARM. In general all run times can be improved. If you have target to achieve and need support to improve cve run time let us know. 4. The executable is expecting the files from application/data and the json files from the top directory to be present on the board. It is generating several output files that you can download and visualize. [04/02, Onoriu] Regarding color format conversion on cve, please find here a sample doing the conversion from YUV420sp to RGB888p: cve_image_format_conversion_02.04.2025.zip Some details: - using SDK 3.35.0 for target os Linux on V4M - using VSFWK API - currently only YUV420sp to RGB888 planar is implemented, more will follow. - copy the 2 json files to the target board, copy the input image to the target board - after running the sample creates an output image on the target board which you can view using any player supporting rgb888 interleaved. Note that just for displaying I am interleaving on ARM side after CVe finishes, the - CVe is outputting 3 different planes. Cve source code is in r_yuv420sp_to_rgb888p.c Let us know if you have any questions. Regarding your question for resize, please create another ticket for this since it would be an IMR job. | Provide API for color format conversion with CVe | Onoriu/ Youmi |  | SOC-1483
|  | Sharing LDC LUT for AI Recognition Preprocessing | action item for IMR use case online session: Sharing LDC LUT for AI Recognition Preprocessing | On Hold | [04/24, Minchael, Yinghui] holding would be better instead of closing [04/09, Yinghui] Attached is the sample code and a simple ppt as explained. Unfortunately with limit time we can only provide the non-opti method. If you have any question please let me know. HKL1484.zip [04/04, Onoriu] Even it may fit to cve I would only go this way if we have a clear no-go for IMR. Ie. I think we should try to promote IMR and convince Klemove to use it, but of course if they have a use case which is no-go then we can try it on cve. So let's wait for your results and their feedback - anyway I could only start in 3 weeks with this (I'm on holiday for 2 weeks from 14.04 and next week I am busy with image format conversion on cve for Klemove). [04/04, Yinghui] I will try my best to finish the first step as benchmarking their LUT on IMR. However, as I mentioned in IMR training, IMR work with floating coordinate and do bilinear filter by itself automatically according the floating coordinates if bilinear filter is enable, otherwise, the nearest pixel value will be used. Also IMR is a 2D GPU work with meshes not pixel by pixel rendering. Which means the interpolation mentioned by HKL is not exactly the way IMR calculate the pixel value. Calculating and storing such amount of info via any computation unit/memory to just finish the interpolation is wasting resource. But I will try to use IMR to render output image according to this new LUT to at least provide the IMR performance w/o any optimization as first step, if HKL accept the way IMR working but they are not fine with the cache performance then we can continue to the next step as optimization. From my side I will prepare a ppt and sample code after benchmarking for explanations. [04/04, Mincheol (HKL)] Complete data transfer for image + LUT, LUT data structure, (x,y)->(u,v) | Provide LDC optimzied method using IMR | Yinghui/ Youmi |  | SOC-1484
|  | Request code snippet for using EGLImageExternal with NV12 input | action item for IMR use case online session: Could you provide an example code snippet for converting NV12 to RGB888 using GPU? (Preferred language: C/C++) | In Progress | [04/09, Bjoern] this is a code-snippet I use with Yocto Linux (SDK1) on V4H board to display live camera feed processed by ISP in a Top-View sample. 20250409_eglImageExternal_snippet.c Please check if this works for you, I cannot guarantee that BB implemented the user-specific functions in the exact same way as our BSP team, but they got our reference implementation. Please check with BB if you need QNX-specific support for this function. I hope this helps you getting started, | Provide code snippet for using EGLImageExternal with NV12 input | Bjoern Toschi/ Youmi |  | SOC-1496
|  | ospi nor flash(MT35XU01G) uboot dts configuration | ospi nor flash(MT35XU01G) uboot dts configuration | Done | [4/8, Gotthard] usually the flash is not supported by Linux/uboot because there is no need. (OS is using eMMC but not flash). | Provide uboot dts configuration for ospi nor flash | Youmi |  | SOC-1491
|  | Ethernet PHY2 ping doesn't work | PHY2 ping works well | Done | [04/23, Youmi] It works well after HW rework (swap data and clock line) [04/18, Youmi] I've tried adjusting TX and RX delay from 0-3ns, but still ping isn't working. I'm planning to debug it with realtek FAE on 4/24. [04/17, Youmi] In the case of PHY2, it is recognized, but the ping does not work. | Check PHY2 ping operation | Youmi
|  | 2nd option QSPI nor flash bring-up | 2nd option QSPI nor flash bring-up | Done | [04/24, Sungmo] Please stop QSPI nor flash bring-up [04/18, Youmi] A flash writer for 1st option OSPI nor flash will be distributed on 4/22, after which JIRA will be registered [04/18, Jihoon] Request 2nd option QSPI nor flash bring-up | Provide flash writer for QSPI nor flash | Youmi

## Mando_RSP
Milestone
Updated by
25.04.21 |  | Ironhide : 2 ea requested
Opp | No. | Issue title | Issue detail | Status | Update | A/I | PIC | Due date | Remark
RSP (POC) |  | Gen5 dataseet & suggest pin map (camera, lidar, display) | Mando will have a meeting with HW company (DH Autoware). H/W interface will be discussed. | Done | [2/10] Gen5 hardware users manual and board information have been deployed | deploy datasheet and pin map | youmi | 2025-02-12 | SOC-1150
|  | question about ethernet gateway | I'm trying to connect the connection between the FPGA and Lidar, IP Cam, and X5H through the Ethernet interface. Q1) Using the RSwitch3 logic of X5H in the figure below, I would like to ask if it can be configured without a separate switch chip. If possible, I would like to ask if I can receive the relevant reference data. Q2) If you say that you use Ethernet switch chips separately as below, please also review if there is anything that could be problematic with X5H. | Done | [03/06, Matthias] the RSwitch3 is behaving like an external Switch would: It is autonomous and will not involve X5H's CPU. [03/05, Youmi] Please check below customer question. In the structure mentioned in the JIRA description, when using Rswitch3, is it possible to connect the FPGA and LiDAR directly without the involvement of the X5H's CPU, or does the CPU need to receive the data first and then pass it on? [03/04, Matthias] I received a detailed explanation. A1) The topology you have shown can be replaced by the X5H. The documentation is still work in progress, attached are two extracts from our material. A2) There are some details to be considered with this setup. As can be seen in the "X5H-RSW3.0-Block.png", the physical pins of the device are shared by a "Lane Selector" with other interfaces by a multiplexer (USB3, PCIe, ETH) This way, for a typical use case, you will only have 4 ethernet ports (ETHA0 .. ETHA3) available, see "X5H-RSW3.0-Ports.png", the remaining lanes will provide PCIe and USB3. But this would still be fine you you application. Another detail is about the PHYs that can be used with the device. This part is still under work, but there is at least an 1Gbps (RMII) and 10Gbps (HSGMII) PHY supported. Q) Do you already have specific requirements regarding the speed of the external interfaces? Then I can try to filter for possible interfaces for your usecase. | answer customer questions | Matthias |  | SOC-1246
|  | Question about AI HWA | The RSP task we are working on is to develop a road surface judgment AI model 1) Acquire learned AI models through dataset construction and learning. (AI models apply CNN, RNN, Transformer, etc.) 2) We aim to port the trained AI model to the AI HW accelerator. At this time, I heard that in order to make good use of the AI HW accelerator, it is necessary to check the AI framework supported by the AI accelerator and in some cases, to convert the AI model to work with the AI accelerator. Please guide me related to this. | Done | [03/06, Youmi] R-Car supports the ability to transform AI models to operate on AI accelerators through Hybrid Compilers (HyCo). https://www.renesas.com/en/software-tool/hybrid-compiler-hyco The HyCo data expressed in detail from the Gen5 AI perspective are as follows. Gen5 utilizes NPX6 (NPU) + VPX5 (DSP) for AI. Shared 1 sheet of hybrid computer for Gen5 | offer HyCo information for Gen5 | youmi
|  | Request for data for HW design | I received the following request for data from DH Autoware. Data transfer related to the X5H EVM board is required. - X5H Specifications - Design Guide - Reference Circuit - PCB Data | Done | [04/01, Gotthard] customer can request access by this links: [RCG5 X5H HW Evaluation Board Secure Content ¦ Renesas¦https://www.renesas.com/en/secure/rcg5-x5h-hw-evaluation-board-secure-content] [RCG5 X5H Series Extended Secure Content ¦ Renesas¦https://www.renesas.com/en/secure/rcg5-x5h-series-extended-secure-content#downloads] | Deliver HW design information | youmi |  | SOC-1463
|  | HL Mando RSP AI Concept and Related Inquiries | Please refer to the attached RSP AI concept first. RSP Diagram-20250328_ Renesas.pptx Q1) It is equipped with various sensors such as 8MP RGB Camera, Thermal Imaging Camera, ML-X LiDAR, and MARWIS as you can see 1page. Does X5 provide the ability to synchronize each sensor? Q2) It is a method of recognizing the road surface condition in the form of classification after dividing the road into patch (pages 2-5 in the attached document). Please review whether there is any performance problem in implementing the attached RSP AI concept in X5. Q3) Does it support HWA to do a preprocessor to divide Patch and Cell? | Open | [04/21, Youmi] No update | answer customer questions | youmi |  | SOC-1464
|  | Maximum number of LIN, IMU, eMMCs supported | Maximum number of LIN, IMU, eMMCs supported | Done | [04/01, Gotthard] X5H/X5M 16xLIN 1xeMMC (+ 2xUFS) X5L/X5B 16xLIN 1xeMMC (+ 1xUFS) Please note this is tentative specification and subject to be changed at any time w/o notice. Documentation will be updated after X5H WS is available. | answer customer questions | youmi |  | SOC-1465
|  | Can CAN and LIN be controlled in CA core? | Can CAN and LIN be controlled in CA core? | In Progress | [04/08, Amulya] I have asked the BSP responsible for info about plans of supporting these on CA core. I will update as soon as I get a feedback. [03/01, Youmi] When using RoX WhiteBox at the customer meeting, we informed that FreeRTOS is provided for CR core and provides CAN/LIN related functions. However, we received the opinion that Mando would like to implement the function in CA core instead of using CR core if possible due to customer resource issue. [03/31, Amulya] According to our SW concept explained in the Golden presentation, the CAN, LIN modules are handled in the CR core. I am not sure if the drivers will be prepared to be controlled by the CA core. Could you please explain why they don't want to use the CR cores? | answer customer questions | youmi |  | SOC-1466
|  | Guide to evaluating StradVision AI solutions | Basically, HL Mando plans to develop its own AI solution with Illinois Tech. HL Mando is also willing to evaluate StradVision AI with Plan B. Please guide HL Mando on how to evaluate Stradvision AI. | In progress | [04/01, Jan] Gen5 AI will be supported by Motoki Kimura (REL/JP)-san and Tomochika Murakami (REL/JP)-san. For more general/strategic topics, I assume someone from Cyril Cordoba's teams needs to get involved too. [04/01, Eric] In case Mando is interesting in AI on Gen5, We have to disucss more in details. 2 items ; Gen5 AI Solution I m not sure what you have explain to Mando (I have the request to provide AI solution on Gen5 - Sorry for delayed answer). This shall be priority one, and we have to better understand thy exact plan. If required, we should have meeting with Mando to explain our situation. Last Time I invited Kimura San for HKMC meeting, he might be the right guy to explain. but it depend on the level of expertise of Mando? Jan , any other idea ? Stradvision As you know, we are under discussion with Stravision to port their SW on our Gen5 Product on H2 2025. We had already deep dive meeting with them to explain our AI Solution for Gen5, but at the moment , Stradvison can hardly comment on the real performance, they can obtain on Gen5. they use Transformer instead of CNN (so different network than V4H) Renesas has Change from Ceva to Synopsis (so no track record on Renesas performance) Having said, that they can explain their superiority of their solution toward their competitor. There I would suggest to loop in Stradvision on that discussion, and having a 3 party meeting. | Guide to evaluate StradVision | youmi |  | SOC-1467

## Kefico
Updated by
25.01.13
Opp | No. | Issue title | Issue detail | Status | Update | A/I | PIC | Due date | Remark
HPVC POC | 1
1

## SL
Updated by
25.01.13
Opp | No. | Issue title | Issue detail | Status | Update | A/I | PIC | Due date | Remark
DSM | 1
1