## 표지
SCOPE OF APPLICATION All Project/Supporting | [6 empty] | Doc. No
Responsibility: 차량SW제품1실 |  | -
MCU별 AUTOSAR SWP 기능 지원 현황
Document Change History
| Date(YYYY-MM-DD) | Ver. | Editor | Chap | 내용(개정 전 -> 개정 후)
| 2016-03-16 | 1.0 | 백종현 | All | 신규 작성
| 2017-10-18 | 2 | 백종현 | All | 17년 성과 및 '18년 계획 반영
| 2018-01-10 | 2.1 | 백종현 | All | RH850/F1KM-S4 디바이스 구체화, Supported Module 일부 일정 수정
| 2018-02-05 | 2.2 | 백종현 | All | RH850/F1KM-S4 의 HSM 일정 변경
| 2018-07-25 | 2.3 | 백종현 | All | 18년 상반기 모듈 일정 계획 반영
| 2019-04-11 | 2.4 | 백종현 | All | 19년 상반기 모듈 일정 계획 반영
| 2019-07-31 | 2.5 | 백종현 | All | 19년 개발 현황 반영, Eth 미지원 in Traveo II, RegMon 지원 범위 변경
| 2020-01-31 | 2.6 | 백종현 | All | 19년 개발 결과, '20년 개발 계획 반영
| 2020-04-10 | 2.7 | 유승훈 | All | 20년 1분기 개발 결과, '20년 2~3분기 개발 계획 반영, RegMon 삭제
| 2020-07-02 | 2.8 | 유승훈 | All | 20년 2분기 개발 결과, '20년 3~4분기, '21년 개발 계획 반영
| 2021-03-03 | 2.9 | 유승훈 | All | 20년 3~4분기 개발 결과, '21년 개발 계획 반영
| 2022-06-23 | 3 | 김회민 | All | 22년 1~2분기 개발 결과 반영, Supported Module 일부 일정 수정
| 2022-06-23 | 3.1 | 김회민 조준호 | All | 22년 3분기 개발 결과 반영
| 2022-12-31 | 3.2 | 조준호 | All | 22년 4분기 개발 결과 반영
| 2023-04-10 | 4 | 김회민 조준호 | All | 23년 1분기 개발 결과 반영 문서 양식 개정
| 2023-07-04 | 4.1 | 김회민 조준호 | All | 23년 2분기 개발 결과 반영
| 2023-07-17 | 4.2 | 김회민 | All | CtrlRam 지원 여부 수정 (Classic 1.0 및 일부 Hybrid 로 한정)
| 2023-08-08 | 4.2.1 | 김회민 | All | OTA/FBL SoC 정책 업데이트
| 2024-01-10 | 4.3.0 | 김회민 조준호 | All | 23년 4분기 개발 결과 반영
| 2024-12-19 | 4.3.1 | 왕혁 | All | 24년 4분기 개발 결과 반영
| 2025-01-14 | 4.3.2 | 왕혁 | All | 25년 1월 개발 결과 반영, U2A8의 이더넷 사용 추가
| 2025-02-26 | 4.3.3 | 왕혁 | All | 25년 2월 개발 결과 반영, CYT3BB 이더넷 사용 추가, 10Base-T1s 내용 추가, RamTst/RomTst의 R403에만 해당으로 내용 수정
| 2025-04-16 | 4.4 | 왕혁 | All | 25년 4월 개발 결과 반영, Notes sheet 추가, TVII MCU Part No. 최신화
| 2025-04-25 | 4.4.1 | 왕혁 | All | FBL, OTA 관련 내용 수정
| 2025-07-18 | 4.4.2 | 왕혁 | All | AUTOSAR Version (4.0.3/4.4.0) -> mobilgene Classic Version (mC1.0/2.0) 변경 S32K142 삭제 및 NXP/Renesas FBL 적용 버전 명기 SecOC 배포 문구 추가. 신규 MCU (Telechips VCP3, AXON) 추가. 메모리 사용량 업데이트 (TC39x, CYT4BF, S32K314).
| 2025-08-08 | 4.4.3 | 왕혁 | All | FBL 관련 내용 수정. LinNm, EthSwt 모듈 삭제. 10Base-T1s 호환성 검토 완료 MCU 정보 Notes sheet에 추가.
| 2025-08-25 | 4.4.4 | 왕혁 | All | DoIP 지원 관련 내용 수정 (Endian 이슈 해결 완료). SecOC 관련 Notes sheet 정보 수정.
27th Edition Date : 2025-08-25 |  |  | File Name : SR_현대 AUTOSAR Classic 플랫폼_(연도)_(분기)_(배포일자)_(revision).xlsx |  |  |  | Creation | Check | Approval
배포 경로: https://ecody-ims.autoever.com/browse/CPINFO-2451 | [6 empty] | 왕혁 | 이영윤 | 클래식오토사1팀장
|  |  | OS Profiler |  |  | '23.09
TBC

## Supported Modules
1. Supported MCU and Compiler
| Category | Module | MCU Supplier | NXP |  |  |  | AURIX 1G |  |  |  | AURIX 2G |  |  |  |  | Renesas | [5 empty] | ST Micro |  |  |  | Cypress |  |  |  |  | Telechips |  | Notes (Documented Date: 2025.05.26)
|  |  | Details | Bolero | S32K14x | S32K31x | S32G | AURIX 3 | AURIX 6 | AURIX 7 | AURIX 9 | AURIX 2G 3 | AURIX 2G 6 | AURIX 2G 7 | AURIX 2G 8 | AURIX 2G 9 | RH850 /F1L | RH850 /F1K (2M) | RH850 /F1KM -S1 | RH850 /F1KM -S2 | RH850 /F1KM -S4 | RH850 /U2A | Chorus (1M/1.5M) | Chorus (2M) | Chorus (3M/4M) | Chorus (6M/8M/10M) | Traveo II (B-E-1M/2M) | Traveo II (B-E-4M) | Traveo II (B-H-4M) | Traveo II (B-H-8M) | Traveo II (B-H-16M) | VCP3 | AXON
1 | mobilgene Classic Version |  |  | mC1.0 |  | mC1.0/2.0 | mC2.0 | mC1.0 |  |  |  | mC2.0 | mC1.0/2.0 | mC2.0 | mC1.0/2.0 | mC1.0/2.0 | mC1.0 |  |  |  |  | mC2.0 | mC1.0 |  |  |  | mC1.0/2.0 |  |  |  | mC2.0 | mC2.0 |  | mC1.0 : mobilgene Classic 1.0 (구 4.0.3) mC2.0 : mobilgene Classic 2.0 (구 4.4.0) For MCUs that are supported by both mobilgene Classic 1.0 and mobilgene Classic 2.0, it is recommended to distribute SWP with mobilgene Classic 2.0, and unless otherwise specifically agreed upon, SWP will be distributed with mobilgene Classic 2.0.
2 | MCU Part No. |  |  | MPC5602C, MPC5603C, MPC5604B, MPC5604C, MPC5604C, MPC5605B, MPC5606B, MPC5607B | S32K144, S32K146, S32K148 | S32K312, S32K314 | S32G274A | TC233L, TC234L, TC237L | TC264D, TC265D, TC267D | TC275T, TC277T | TC297T, TC298T, TC299T | TC337x, TC336x, TC334x, TC333x, TC332x | TC367x, TC366x, TC365x, TC364x | TC377x, TC375x | TC387x, TC389x | TC397x, TC397x_ADAS, TC399x | R7F701002, R7F701003, R7F701008, R7F701009, R7F701010, R7F701013, R7F701014, R7F701015, R7F701016, R7F701017, R7F701018, R7F701019, R7F701020, R7F701021, R7F701022, R7F701023, R7F701024, R7F701025, R7F701030, R7F701031, R7F701032, R7F701033, R7F701034, R7F701035, R7F701046, R7F701049, R7F701053 | R7F701542, R7F701543, R7F701546, R7F701547, R7F701557, R7F701560, R7F701561, R7F701562, R7F701563, R7F701566, R7F701567, R7F701577, R7F701580, R7F701581, R7F701582, R7F701583, R7F701586, R7F701587, R7F701597, R7F701602, R7F701603, R7F701610, R7F701611, R7F701612, R7F701613, R7F701620, R7F701621, R7F701622, R7F701623 | R7F701684, R7F701685, R7F701686, R7F701687, R7F701688, R7F701689, R7F701690, R7F701691, R7F701692, R7F701693, R7F701694, R7F701695, | R7F701760, R7F701762, R7F701764 | R7F701634, R7F701635, R7F701636, R7F701637, R7F701638, R7F701639, R7F701640, R7F701641, R7F701642, R7F701643, R7F701644, R7F701645, R7F701646, R7F701647, R7F701648, R7F701649, R7F701650, R7F701651, R7F701652, R7F701653 | R7F702301 (U2A8) | 1M : SPC584B60 1.5M SPC584B64 | SPC584B70, SPC584C70, SPC58EC70 | 3M : SPC584C74, SPC58EC74 4M : SPC584C80, SPC58EC80 | 6M : SPC58NH84 8M : SPC58NH90 10M : SPC58NH92 | CYT2B73BAD, CYT2B73CAD, CYT2B74BAD, CYT2B74CAD, CYT2B75BAD, CYT2B75CAD, CYT2B77BAD, CYT2B77CAD, CYT2B78BAD, CYT2B78CAD, CYT2B93BAC, CYT2B93CAC, CYT2B94BAC, CYT2B94CAC, CYT2B95BAC, CYT2B95CAC, CYT2B97BAC, CYT2B97CAC, CYT2B98BAC, CYT2B98CAC | B-E-4M : CYT2BL3BAA, CYT2BL3CAA, CYT2BL4BAA, CYT2BL4CAA, CYT2BL5BAA, CYT2BL5CAA, CYT2BL7BAA, CYT2BL7CAA, CYT2BL8BAA, CYT2BL8CAA | CYT3BB5CEB, CYT3BB7CEB, CYT3BB8CEB, CYT3BBBCEB CYT4BB5CEB, CYT4BB7CEB, CYT4BB8CEB, CYT4BBBCEB | CYT4BF8CDD, CYT4BF8CED, CYT4BFBCHD, CYT4BFBCJD, CYT4BFCCHD, CYT4BFCCJD | CYT6BJ8DDE, CYT6BJ8DDS, CYT6BJ8DEE, CYT6BJ8DES, CYT6BJBDHE, CYT6BJBDHS, CYT6BJBDJE, CYT6BJBDJS, CYT6BJCDHE, CYT6BJCDHS, CYT6BJCDJE, CYT6BJCDJS | TCC712x, TCC714x | TCN100x
3 | Applicable Compiler |  |  | Green Hills |  |  |  | Tasking |  |  |  | Tasking |  |  |  |  | Green Hills | [5 empty] | Green Hills |  |  |  | Green Hills |  |  |  |  | Tasking
2. Standard Modules
| Category | Module | MCU Supplier | NXP |  |  |  | AURIX 1G |  |  |  | AURIX 2G |  |  |  |  | Renesas | [5 empty] | ST Micro |  |  |  | Cypress |  |  |  |  | Telechips |  | Notes
|  |  | Details | Bolero | S32K14x | S32K31x | S32G | AURIX 3 | AURIX 6 | AURIX 7 | AURIX 9 | AURIX 2G 3 | AURIX 2G 6 | AURIX 2G 7 | AURIX 2G 8 | AURIX 2G 9 | RH850 /F1L | RH850 /F1K (2M) | RH850 /F1KM -S1 | RH850 /F1KM -S2 | RH850 /F1KM -S4 | RH850 /U2A | Chorus (1M/1.5M) | Chorus (2M) | Chorus (3M/4M) | Chorus (6M/8M/10M) | Traveo II (B-E-1M/2M) | Traveo II (B-E/H-4M) | Traveo II (B-H-4M) | Traveo II (B-H-8M) | Traveo II (B-H-16M) | VCP3 | AXON
1 | OS | Os | SC1 | O |  |  |  | O |  |  |  | O |  |  |  |  | O |  |  |  |  | O | O |  |  |  | O |  |  |  |  | O
|  |  | SC2 | O |  |  |  | O |  |  |  | O |  |  |  |  | X |  |  |  |  | O | X |  |  |  | O |  |  |  |  | O
|  |  | SC3 | O |  |  |  | O |  |  |  | O |  |  |  |  | X |  |  |  |  | O | X |  |  |  | O |  |  |  |  | O
|  |  | SC4 | O |  |  |  | O |  |  |  | O |  |  |  |  | X |  |  |  |  | O | X |  |  |  | O |  |  |  |  | O
|  |  | Multi-Core | N/A |  |  | O | N/A | O |  |  | N/A | O |  |  |  | N/A |  |  |  |  | O | O |  |  |  | N/A | O |  |  |  | N/A
2 | RTE | Rte |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
3 | SYS | BswM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
4 |  | EcuM |  | O |  |  | O1) | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O |  | 1) S32G Sleep-WakeUp is not Supported
5 |  | Wdg |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O |  | Refer to the supported devices
6 |  | WdgIf |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
7 |  | WdgM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
8 | MEM | NvM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
9 |  | MemIf |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
10 |  | Ea |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
11 |  | Eep |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O |  | Refer to the supported devices
12 | DIAG | Dcm | General | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
|  |  | Secure Access | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
13 |  | Dem |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
14 |  | FiM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
15 |  | Det |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
16 | COM | Com |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
17 |  | ComM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
18 |  | PduR |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
19 |  | IpduM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
20 |  | Nm |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
21 |  | LdCom |  | X |  |  |  | X |  |  |  | O1) |  |  |  |  | X | [5 empty] | X |  |  |  | X |  |  |  |  | X |  | 1) Supported by AR4.4 LdCom module
22 |  | ComXf |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
23 |  | Xcp | DAQ,CAL,STIM | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
|  |  | PROG | O | X |  |  | O |  |  |  | O |  |  |  |  | X | [5 empty] | X |  |  |  | X |  |  |  |  | X
24 | CAN | CanNm |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
25 |  | CanSM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
26 |  | CanTp |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
27 |  | CanTrcv |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O |  | Refer to the supported devices
28 |  | CanIf | General | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
|  |  | CAN FD | N/A | O |  |  | O |  |  |  | O |  |  |  |  | N/A | O |  |  |  |  | O |  |  |  | O |  |  |  |  | O
29 | LIN | LinIf |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
30 |  | LinSm |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
31 |  | LinTrcv |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O |  | Refer to the supported devices
32 | ETH | DoIp |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O |  | O |  |  |  | N/A |  | O |  | N/A | O |  | No use cases
33 |  | SoAd |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O | O | O |  |  |  | N/A |  | O |  | N/A | O
34 |  | EthIf |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O | O | O |  |  |  | N/A |  | O |  | N/A | O
35 |  | EthSM |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O | O | O |  |  |  | N/A |  | O |  | N/A | O
36 |  | EthTrcv |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O | O | O |  |  |  | N/A |  | O |  | N/A | O |  | Refer to the supported devices Eth MCAL does not support the SPI, only RMII MAC PHY is supported.
37 |  | TcpIp |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O | O | O |  |  |  | N/A |  | O |  | N/A | O
38 |  | UdpNm |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O | O | O |  |  |  | N/A |  | O |  | N/A | O
39 |  | SD |  | N/A |  |  | O1) | O1) |  |  |  | O1) |  |  |  |  | N/A |  |  |  | O1) | O | O1) |  |  |  | N/A |  | O |  | N/A | O |  | 1) Supported by AR4.4 SD module
40 |  | SomeIpXf |  | N/A |  |  | O1) | O1) |  |  |  | O1) |  |  |  |  | N/A |  |  |  | O1) | O | O1) |  |  |  | N/A |  | O |  | N/A | O |  | 1) Supported by AR4.4 SomeIpXf module
41 |  | SomeIpTp |  | N/A |  |  | O1) | O1) |  |  |  | O1) |  |  |  |  | N/A |  |  |  | O1) | O | O1) |  |  |  | N/A |  | O |  | N/A | O |  | 1) Supported by AR4.4 SomeIpTp module
42 | J1939 | J1939Tp |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
43 |  | J1939Dcm |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
44 |  | J1939Nm |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
45 |  | J1939Rm |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
46 | SEC | Csm |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
47 |  | SecOC |  | △ |  |  |  | △ |  |  |  | △ |  |  |  |  | △ | [5 empty] | △ |  |  |  | △ |  |  |  |  | △ |  | Provisional module release: 25. 5/E Official release: 25. 9 (expected date)
48 |  | Crc |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
49 |  | E2E |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
50 |  | E2EXf |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
51 |  | RamTst |  | O1) |  |  | X | O |  |  |  | O1) |  |  |  |  | O |  |  |  |  | X | O |  |  |  | O1) |  |  |  | X | O |  | 1) RamTst is only supported in 4.0.3 (Classic 1.0)
3. Non-Standard BSW Modules
| Category | Module | Details | Bolero | S32K14x | S32K31x | S32G | AURIX 3 | AURIX 6 | AURIX 7 | AURIX 9 | AURIX 2G 3 | AURIX 2G 6 | AURIX 2G 7 | AURIX 2G 8 | AURIX 2G 9 | RH850 /F1L | RH850 /F1K (2M) | RH850 /F1KM -S1 | RH850 /F1KM -S2 | RH850 /F1KM -S4 | RH850 /U2A | Chorus (1M/1.5M) | Chorus (2M) | Chorus (3M/4M) | Chorus (6M/8M/10M) | Traveo II (B-E-1M/2M) | Traveo II (B-E/H-4M) | Traveo II (B-H-4M) | Traveo II (B-H-8M) | Traveo II (B-H-16M) | VCP3 | AXON | Notes
1 | IO | IoHwAb |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O |  | Refer to the supported devices
2 |  | MuxDemuxIf |  | O |  |  | X | O |  |  |  | O |  |  |  |  | O |  |  |  |  | X | O |  |  | X | O | X |  |  |  | O
3 |  | OCU |  | O | X |  | O | X |  |  |  | X |  |  |  |  | O |  |  |  |  | X | O |  |  |  | X | O |  |  |  | O |  | MCAL Functionality
4 | COM | OsekNm |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
5 |  | UART |  | O | X |  |  | N/A |  |  |  | N/A |  |  |  |  | O | [5 empty] | X |  |  |  | X |  |  |  |  | X |  | MCAL Functionality
6 |  | CDD_Router |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O |  | Sample Router CDD
7 | SYS | Pm |  | O | X |  |  | X |  |  |  | X |  |  |  |  | O |  |  |  |  | X | X |  |  |  | X |  |  |  |  | X
8 |  | CoSvAb |  | O | X |  |  | O |  |  |  | X |  |  |  |  | O |  |  |  |  | X | O |  |  | X | X |  |  |  |  | X
9 | SEC | CtrlRAM1) |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | X |  | 1) Only supported in 4.0.3 (Classic 1.0)
11 |  | RomTst |  | O1) |  |  | X | O |  |  |  | O1) |  |  |  |  | O |  |  |  |  | X | O |  |  |  | O1) |  |  |  |  | X |  | 1) RomTst is only supported in 4.0.3 (Classic 1.0)
12 | OS | Imp_Os | CPU Load | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
|  |  | OS Profiler | O |  |  | '23.09 | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
|  |  | Exception Handler | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
4. HMC Specific Modules
| Category | Module | Details | Bolero | S32K14x | S32K31x | S32G | AURIX 3 | AURIX 6 | AURIX 7 | AURIX 9 | AURIX 2G 3 | AURIX 2G 6 | AURIX 2G 7 | AURIX 2G 8 | AURIX 2G 9 | RH850 /F1L | RH850 /F1K (2M) | RH850 /F1KM -S1 | RH850 /F1KM -S2 | RH850 /F1KM -S4 | RH850 /U2A | Chorus (1M/1.5M) | Chorus (2M) | Chorus (3M/4M) | Chorus (6M/8M/10M) | Traveo II (B-E-1M/2M) | Traveo II (B-E/H-4M) | Traveo II (B-H-4M) | Traveo II (B-H-8M) | Traveo II (B-H-16M) | VCP3 | AXON | Notes
1 | CAN | CanCM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
2 | COM | EthDiag |  | N/A | O |  |  | O |  |  |  | O |  |  |  |  | N/A | O |  |  |  |  | O |  |  |  | N/A |  |  |  |  | O
3 | COM | EthCC |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O |  | O |  |  |  | N/A |  | O |  | N/A | O
4 | COM | EthNM |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O |  | O |  |  |  | N/A |  | O |  | N/A | O
5 | COM | EthTP |  | N/A |  |  | O | O |  |  |  | O |  |  |  |  | N/A |  |  |  | O |  | O |  |  |  | N/A |  | O |  | N/A | O
6 | SEC | IdsM |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
5. Indivisual SW Solution note) In the case of System-on-Chip (SoC), OTA/FBL is not supported by default. In case of separate consultation, please contact the project manager. note) ES98765-02(CCU2) is supported in FBL3.0.
| Category | Module | Details | Bolero | S32K14x | S32K31x | S32G | AURIX 3 | AURIX 6 | AURIX 7 | AURIX 9 | AURIX 2G 3 | AURIX 2G 6 | AURIX 2G 7 | AURIX 2G 8 | AURIX 2G 9 | RH850 /F1L | RH850 /F1K (2M) | RH850 /F1KM -S1 | RH850 /F1KM -S2 | RH850 /F1KM -S4 | RH850 /U2A | Chorus (1M/1.5M) | Chorus (2M) | Chorus (3M/4M) | Chorus (6M/8M/10M) | Traveo II (B-E-1M/2M) | Traveo II (B-E/H-4M) | Traveo II (B-H-4M) | Traveo II (B-H-8M) | Traveo II (B-H-16M) | VCP3 | AXON | Notes
1 | FBL |  | FBL-CAN | O |  |  | N/A | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O | N/A | FBL-Sec Flash 2.0 depends on HSM support FBL2.0 is not supported. Only FBL3.0 is avaliable.
|  |  | FBL-CANFD | N/A | O |  |  | O |  |  |  | O |  |  |  |  | N/A | O |  |  |  |  | O |  |  |  | O |  |  |  |  | O
|  |  | FBL-Ethernet | N/A |  | X |  | X |  |  |  | O |  |  |  |  | N/A |  |  |  | X | O | O |  |  |  | N/A |  |  |  |  | N/A
|  |  | FBL-ASK (H-SAC) | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
|  |  | FBL-Sec Access 1.0 (C-SAC) | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
|  |  | FBL-Sec Access 2.0 (C-SAC) | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O
|  |  | FBL-Sec Flash 2.0 | N/A |  | O |  | O |  |  |  | O |  |  |  |  | N/A |  | O |  |  |  | O |  |  |  | O |  |  |  |  | O
2 | OTA |  | Diagnostic(Basic) | O |  |  |  | O |  |  |  | O |  |  |  |  | O | [5 empty] | O |  |  |  | O |  |  |  |  | O |  | Update through FBL from Master ECU (ex. CCU) by OTA method
|  |  | Memory-Swap | N/A |  | O (S32K311 : N/A) | N/A | N/A |  |  |  | N/A | O |  |  |  | N/A |  | X | O | O | O | X | X | 3M : SPC584C74 : O SPC58EC74 : O 4M : SPC584C80 : O SPC58EC80 : O | 6M : SPC58xH84 : O 8M : SPC58xH90 : O 10M : SPC58xH92 : O | O |  |  |  |  | N/A | N/A | 1) Update through DualM from Master ECU (ex. CCU) by OTA method. 2) If the ROM size is less than 1M, Memory-Swap cannot be used.
|  |  | Compression |  |  | O | [5 empty] | O | [6 empty] | X | O | O | O | X | X | 3M : SPC584C74 : O SPC58EC74 : O 4M : SPC584C80 : O SPC58EC80 : O | 6M : SPC58xH84 : O 8M : SPC58xH90 : O 10M : SPC58xH92 : O | O |  |  |  |  | O |  | 1) Diagnostic(Basic) + Compression 2) Memory-Swap + Compression. 3) If the ROM size is less than 1M, Memory-Swap cannot be used. 4) S32K311, AURIX 2G 3 is not supported in Memory-Swap
6. Memory Usage(Kb)
note) This information is reference only - the actual total memory usage is dependant to the requirement(including Mcal SW), stacks composition, and any further variants of the SWP. It does not include Application SW memory usage.
| Category | Module | Details | Bolero | S32K14x | S32K31x | S32G | AURIX 3 | AURIX 6 | AURIX 7 | AURIX 9 | AURIX 2G 3 | AURIX 2G 6 | AURIX 2G 7 | AURIX 2G 8 | AURIX 2G 9 | RH850 /F1L | RH850 /F1K (2M) | RH850 /F1KM -S1 | RH850 /F1KM -S2 | RH850 /F1KM -S4 | RH850 /U2A | Chorus (1M/1.5M) | Chorus (2M) | Chorus (3M/4M) | Chorus (6M/8M/10M) | Traveo II (B-E-1M/2M) | Traveo II (B-E/H-4M) | Traveo II (B-H-4M) | Traveo II (B-H-8M) | Traveo II (B-H-16M) | VCP3 | AXON | Notes
1 | RTSW |  | ROM | 238 | 424 | 518 | N/A | 304 | 312 | 372 | 372 | 504 | 644 | 644 | 708 | 595 | 416 | 488 | 479 | - | 484 | - | 351 | 584 |  | 580 | 448 | 392 | 392 | 830 | 545 | - | -
|  |  | RAM | 21 | 128 | 140 | 2008 | 64 | 64 | 64 | 64 | 112 | 148 | 148 | 148 | 180 | 32 | 32 | 46 | - | 46 | - | 65 | 192 |  | 132 | 24 | 20 |  | 238 | 78 | - | -
2 | FBL |  | ROM | 256 |  | 262 | TBC | 256 |  |  |  | 256 | - | - | - | 255 | 256 | [5 empty] | 256 |  |  |  | 256 | - | - | 267 | - | - | -
|  |  | RAM | 64 |  | 88 | - | 40 |  |  |  | 40 | - | - | - | 110 | 64 |  | 32 | - | 40 | - | 40 | 40 |  | 72 | 36 | - | - | 145 | - | - | -
Disclaimer
- License Agreement is needed in some Security Modules (SecOC, HSM, Secure Access, Secure Flash) - Since MCUs other than Bolero and RH850F1L/K/KM have significantly different low power support functions depending on the architecture, please contact AutoEver before selecting an MCU. - MCAL license is not included in scope of platform offering. MCAL license for mass production must be purchased separately if necessary. - The warranty for MCAL is not included in the scope of SWP delivery. - In the case of MCUs whose HSMs are provided by 3rd parties, only standardized interfaces are provided for the application of Secure Flash 2.0 so that partners can integrate functions. - Ethernet modules of CYT3BBx can be available when supporing Eth MCAL.
Legend
O:Available/Applicable △:Partially Available (Refer to its note) TBC:To Be Confirmed 'YY/MM:Release Month Confirmed -:Not Applicable

## Notes
Item | DDS
Related FAQ | [Eth][R44] DDS mobilgene 2.0 포팅 가이드 - mobilgene Classic FAQ - eCoDY-ECM
Contents (Kor/Eng) | DDS관련 DB는 기존 Eth DB와 별도로 필요함. 가이드 참조. | DDS-related DB is required separately from existing Eth DB. Refer to Porting Guide.
| DDS 솔루션은 고객사 자체 통합 필요하며, RAM 사용량 체크 필요 (SWP+DDS+App). RTI 가이드 상 300K~1M 필요 (Sturcture 개수, 설정 파라메터에 따라 상이). | DDS solutions must be integrated directly by customer (Tier) themselves. Check RAM usage (SWP+DDS+App) is essential to use DDS. 300K to 1M required from RTI guide (dependent on number of structure, setting paramter).
Remark | Min. Requirements of memory usage for RTI DDS. RAM : HMC XML (52 struct.) 270KB + CDD 200KB = 470KB ROM : CDD 150KB
Item | ES98765-02 사양 적용
Related FAQ | [Fota][SAG] ES98765-02 - mobilgene Classic FAQ - eCoDY-ECM
Contents (Kor/Eng) | 1.RTSW는 FOTA적용 필요(CCU 2세대). 2.FBL3.0 적용 필수(CCU 2세대). FBL3.0 적용 시 NvM 미지원. | 1. RTSW is highly recommended to applying FOTA (CCU 2nd generation). 2. It is highly recommended to applying FBL3.0 (CCU 2nd generation). When applying FBL3.0, NvM is not supported.
| 해당 사양은 2세대 OTA 사양으로 물리 레이어 (Ethernet 10/100/1000Base, CAN/CAN-FD 등)와 무관. | This specification is the 2nd generation OTA specification and is independent of the physical layer (Ethernet 10/100/1000Base, CAN/CAN-FD, and so on).
Remark
Item | 다운그레이드 방지 및 OEUK 적용
Related FAQ | [OEUK][R4X] IM - mobilgene Classic FAQ - eCoDY-ECM
[Dcm][R40][SAG] OEUK Configuration with Csm R44_Async - mobilgene Classic FAQ - eCoDY-ECM
Contents (Kor/Eng) | 메모리 이중화 사용 시 (FBL 3.0 또는 RTSW), 메모리 이중화 미 사용시 (FBL 3.0) | If the memory redundant system is used: FBL 3.0 or RTSW If the memory redundant system is not used: FBL 3.0
| FBL 3.0은 Dcm 모듈에 OEUK 구성함. 참고로, Dcm_R40과 CryptoStack R44를 이용해 OEUK 설정 | OEUK is configured within the DCM module for FBL 3.0. For reference, OEUK can be set by using Dcm_R40 and CryptoStack R44.
Remark
Item | FBL
Related FAQ | [Fota] Module FAQ - mobilgene Classic FAQ - eCoDY-ECM
Contents (Kor/Eng) | 오토에버 FBL 솔루션은 FAQ 내에 상세 구조 참고. | See detailed structure within FAQ for HAE FBL solution.
| 이후의 사양 대응 (ES98765-02 등)은 FBL 3.0을 통해 이루어짐. | OEUK and later specifications (ES98765-02, etc.) are only available through FBL 3.0.
Remark
Item | SecOC
Related FAQ | [SecOC][R44] - mobilgene Classic FAQ - eCoDY-ECM
Contents (Kor/Eng) | SecOC 모듈과 Crypto Stack (CryIf, Csm, KeyM, Crypto Driver) 모두 R44 모듈 필요함 그리고, HAE 차량SW보안기술팀에서 배포하는 FvM/AppKeyM 모듈 적용이 필요함. | Both the SecOC module and the crypto stack (CryIf, CSM, KeyM, Crypto Driver) require R44 modules. In addition, Fvm/AppKeyM module released by HAE Automotive SW Security Techonology Team should be applied.
| SecOC 적용 대상은 CAN msg로 이더넷 제외 (ES95489-71 및 HMC 차량사이버보안개발팀). | SecOC can be operated by CAN msg, not Ethernet (based on ES95489-71 and HMC Vehicle CyberSecurity Development Team).
| SecOC 모듈은 양방향 인증과 독립적임. | The SecOC module is independent of bidirectional authentication.
| ES95489-71 사양 만족을 위해서는 SecOC 모듈과 함께 양방향 인증이 적용된 DCM 모듈이 필요함 (25. 3Q 배포 예정). 하지만, ES95489-01 사양의 단방향 인증만 필요한 경우, 양방향 인증이 적용된 DCM 모듈 불필요함. | A DCM module with the bidirectional authentication (will be released at 25. 3Q) is required along with the SecOC module to satisfy ES95489-71. However, if only the unidirectional authentication of ES95489-01 specification is required, DCM module with the bidirectional authentication is unnecessary.
| 보안 알고리즘은 MAC 사용. SecOC 모듈과 Crypto Driver 간 모듈 의존성은 없지만, ES95489-71 만족을 위해서는 Crypto_76_mSecHSM 사용 권장. | A MAC algorithm is used. There are no module dependency between SecOC and Crypto Driver, however Crypto_76_mSecHSM is recommended to satisfy the ES95489-71.
Remark
Item | mobilgene SWP에 구현된 ES 사양 정보
Related FAQ | SWP에서 구현된 ES 사양 정보 (ES) - mobilgene Classic FAQ - eCoDY-ECM
Contents (Kor/Eng) | - | -
Remark | 빈칸으로 빠져 있는 부분은 개발 완료 되었으나 관련 내용 추가 확인 진행 중, 신규 ES 사양에 대해서 지속 대응 중.
Item | 10Base-T1s 호환성 검토
Related FAQ | [Eth][R44] OtherTrcv(Autoever에서 지원하지 않는) 사용 시 통합 설정/구현 가이드
Contents (Kor/Eng) | 호환성 검토 완료 - CYT4BB/4BF/3BB RMII interface with Microchips LAN8670 - TC39x/TC38x RMII interface with Microchips LAN8670 - U2A/U5L 예정. | Feasibility check - CYT4BB/4BF/3BB RMII interface with Microchips LAN8670 - TC39x/TC38x RMII interface with Microchips LAN8670 - U2A/U5L will be
Remark | 특정 PHY 칩에 대한 10Base-T1s 개발계획은 없음 (플랫폼 배포 시 OtherTrcv로 제공).

## Supported MCU (hidden)
1. Supported MCU and Compiler
Company | MCU | Details | Compiler | CAN | CAN -FD | LIN | ETH | HSM | Notes (Documented Date :2023.03.16)
NXP | Bolero | MPC5602C, MPC5603C, MPC5604B, MPC5604C, MPC5605B, MPC5606B, MPC5607B | Green Hills | O | - | O | - | - | -
| S32K14x | S32K142, S32K144, S32K146, S32K148 | Green Hills | O | O | O | O | - | -
| S32K31x | S32K312, S32K314 | Green Hills | O | O | O | X | O | HSM - NXP HSE
| S32G | S32G274A | Green Hills | O | O | O | O | - | HSM - TBD
Infineon | AURIX 3 | TC233L, TC234L, TC237L | Tasking | O | O | O | O | O | HSM - HAE HSM
| AURIX 6 | TC264D, TC265D, TC267D | Tasking | O | O | O | O | O | HSM - HAE HSM
| AURIX 7 | TC275T, TC277T | Tasking | O | O | O | O | O | HSM - HAE HSM
| AURIX 9 | TC297T, TC298T, TC299T | Tasking | O | O | O | O | O | HSM - HAE HSM
| AURIX 2G 6 | TC367x, TC366x, TC365x, TC364x | Tasking | O | O | O | O | O | HSM - HAE HSM
| AURIX 2G 8 | TC387x, TC387x_ADAS, TC389x | Tasking | O | O | O | O | O | HSM - HAE HSM
| AURIX 2G 9 | TC397x, TC397x_ADAS, TC399x | Tasking | O | O | O | O | O | HSM - HAE HSM
Renesas | RH850/F1L | R7F701002, R7F701003, R7F701008, R7F701009, R7F701010, R7F701013, R7F701014, R7F701015, R7F701016, R7F701017, R7F701018, R7F701019, R7F701020, R7F701021, R7F701022, R7F701023, R7F701024, R7F701025, R7F701030, R7F701031, R7F701032, R7F701033, R7F701034, R7F701035, R7F701046, R7F701049, R7F701053 | Green Hills | O | - | O | - | - | -
| RH850/F1K | R7F701542, R7F701543, R7F701546, R7F701547, R7F701557, R7F701560, R7F701561, R7F701562, R7F701563, R7F701566, R7F701567, R7F701577, R7F701580, R7F701581, R7F701582, R7F701583, R7F701586, R7F701587, R7F701597, R7F701602, R7F701603, R7F701610, R7F701611, R7F701612, R7F701613, R7F701620, R7F701621, R7F701622, R7F701623 | Green Hills | O | O | O | - | - | -
| RH850/F1KM -S1 | R7F701684, R7F701685, R7F701686, R7F701687, R7F701688, R7F701689, R7F701690, R7F701691, R7F701692, R7F701693, R7F701694, R7F701695, | Green Hills | O | O | O | - | - | -
| RH850/F1KM -S4 | R7F701634, R7F701635, R7F701636, R7F701637, R7F701638, R7F701639, R7F701640, R7F701641, R7F701642, R7F701643, R7F701644, R7F701645, R7F701646, R7F701647, R7F701648, R7F701649, R7F701650, R7F701651, R7F701652, R7F701653 | Green Hills | O | O | O | O | O | HSM - HAE HSM
ST Micro | Chorus 4M | SPC58EC80, SPC58EC74, SPC58EC70, SPC584C80, SPC584C74, SPC584C70 | Green Hills | O | O | O | O | O | HSM - HAE HSM
| Chorus 2M | SPC584B70, SPC584B64, SPC584B60 | Green Hills | O | O | O | O | O | HSM - HAE HSM
| Chorus 10M | SPC58NH92, SPC58NH90, SPC58NH84, SPC58NH92, SPC58NH90, SPC58NH84, SPC58NH90, SPC58NH84, SPC58NH92, SPC58NH90, SPC58NH84 | Green Hills | O | O | O | O | O | HSM - HAE HSM
Cypress | Traveo II (B-E-1/2M) | CYT2B73BAE, CYT2B73BAS, CYT2B73CAE, CYT2B73CAS, CYT2B74BAE, CYT2B74BAS, CYT2B74CAE, CYT2B74CAS, CYT2B75BAE, CYT2B75BAS, CYT2B75CAE, CYT2B75CAS, CYT2B77BAE, CYT2B77BAS, CYT2B77CAE CYT2B77CAS, CYT2B78BAE, CYT2B78BAS, CYT2B78CAE, CYT2B78CAS CYT2B93BAE, CYT2B93BAS, CYT2B93CAECYT2B93CAS, CYT2B94BAE, CYT2B94BAS, CYT2B94CAE, CYT2B94CAS, CYT2B95BAE, CYT2B95BAS, CYT2B95CAE, CYT2B95CAS, CYT2B97BAE, CYT2B97BAS, CYT2B97CAE CYT2B97CAS, CYT2B98BAE, CYT2B98BAS, CYT2B98CAE, CYT2B98CAS | Green Hills | O | O | O | X | O | HSM - HAE HSM
| Traveo II (B-E-4M) | CYT2BL3BAE, CYT2BL3BAS, CYT2BL3CAE, CYT2BL3CAS, CYT2BL4BAE, CYT2BL4BAS, CYT2BL4CAE, CYT2BL4CAS, CYT2BL5BAE, CYT2BL5BAS, CYT2BL5CAE, CYT2BL5CAS, CYT2BL7BAE, CYT2BL7BAS, CYT2BL7CAE CYT2BL7CAS, CYT2BL8BAE, CYT2BL8BAS, CYT2BL8CAE, CYT2BL8CAS | Green Hills | O | O | O | X | O | HSM - HAE HSM
| Traveo II (B-H-4M) | CYT3BB5CEE, CYT3BB5CES, CYT3BB7CEE, CYT3BB7CES, CYT3BB8CEE, CYT3BB8CES, CYT3BBBCEE, CYT3BBBCES, CYT4BB5CEE, CYT4BB5CES, CYT4BB7CEE, CYT4BB7CES, CYT4BB8CEE, CYT4BB8CES, CYT4BBBCEE CYT4BBBCES | Green Hills | O | O | O | X | O | HSM - HAE HSM
| Traveo II (B-H-8M) | CYT4BF8CDE, CYT4BF8CDS, CYT4BF8CEE, CYT4BF8CES, CYT4BFBCHE, CYT4BFBCHS, CYT4BFBCJE, CYT4BFBCJS, CYT4BFCCHE, CYT4BFCCHS, CYT4BFCCJE, CYT4BFCCJS | Green Hills | O | O | O | X | O | HSM - HAE HSM
* License Agreement is needed in some Security Modules (SecOC, HSM, Secure Access, Secure Flash) (if NON-HKMC OEM)
* Legend - (O:Available, X:Not Available, 'xx.yy:Planned, -:Not Applicable)
* 'xx.y is the planned SWP release date.

## Description (hidden)
1. Standard Modules
| Category | Module | Description
1 | OS | Os | SW that carry out run unit(Task, Interrupt) by managing authority of CPU control.
2 | RTE | Rte | Perform a role as interface between application and BSW module. It offers communication and scheduling of application and BSW module.
3 | SYS | BswM | Mode managing module. Determines whether the requested mode should be changed based on rules, and performs the action routine(Mode changing etc.) as a result.
4 |  | EcuM | Status managing module of ECU(Wake up, Sleep, Shutdown). Terminates or initialize by ECU status, manages Wakeup Event.
5 |  | Wdg | External watchdog device.(Controlled by toggle pin of constant cycle)
6 |  | WdgIf | WdgM is an abstraction module that allows multiple internal or external watchdog devices to be used through a common interface.
7 |  | WdgM | It monitors the real time monitoring of whether SW is executed according to the set time or sequence and restores the system by a method such as reset when an error occurs.
8 | MEM | NvM | Module that manages NV Data requested by Application and BSW module.
9 |  | MemIf | Module that provides an interface between NvM and each memory device.
10 |  | Ea | Module that controls internal or external EEPROM Device.
11 |  | Eep | External EEPROM device control module. (developed separately for each device - M95 series supported)
12 | DIAG | Dcm | Manage diagnostic data flow, and diagnostic state, Responses after performing diagnostic request from diagnostic unit.(DTC, status information)
13 |  | Dem | A module that processes and stores Diagnostic events (errors, FreezeFrame data, DTC, etc.)
14 |  | FiM | Activation/deactivation of functionality status of application by Permission/inhibit condition (event passed / failed).
15 |  | Det | All errors occurring during BSW development are reported to the DET module and managed.
16 | COM | Com | Provides an interface to transmit and receive data by signal unit by classifying PDU into signal unit.
17 |  | ComM | Control BSW module related to communication. Provides same interface regardless of communication method by encapsulating sub-communication services.
18 |  | PduR | Located between COM and communication layer (TP, ComIf). It performs routing and gateway function to route I-Pdu which is transmitted and received according to Routing Table to the upper and lower layer.
19 |  | IpduM | It is Linked with PduR and is responsible for sending and receiving Multiplexed I-PDU.
20 |  | Nm | Provides interface between bus-specific NM modules and ComM modules. Synchronization Network SLEEP entry of Bus-specific NM module
21 |  | LdCom | A module for efficiently supporting transmission/reception of large data based on byte.
22 |  | ComXf | functionality when the target bus system uses a fixed communication matrix with packed data representations
23 |  | Xcp | Support to ECU Calibration function using CAN, FlexRay, Ethernet protocol.
24 | CAN | CanNm | By communicating with other nodes on the CAN network, Synchronize network SLEEP and control WAKE UP.
25 |  | CanSM | Change to CAN Bus mode requested by ComM. Checks the status of CAN Bus off and restores to normal state when Bus off.
26 |  | CanTp | In the CAN bus data, a large amount of data is fragmented and transmitted, or the received data is reassembled and transferred to the upper module.
27 |  | CanTrcv | Control the operation mode of transceiver which is HW device.
28 |  | CanIf | Module that takes charge of transmitting PDU data received from upper module using CAN frame send function of CAN MCAL Driver, receiving CAN frame on CAN bus and transferring it to upper module.
29 | LIN | LinIf | Transmission and reception of Lin Frame and processing Lin communication mode request received from LinSm.
30 |  | LinNm | Processing of sleep/wakeup state change of Lin communication received from Nm.
31 |  | LinSm | Handles Lin communication mode request received from ComM. Pass the current LIN communication status to the upper module.
32 |  | LinTrcv | Module to control the operation mode of Lin Transceiver (by device).
33 | ETH | DoIp | SoAd is used to diagnose vehicle using Ethernet communication as the upper module.
34 |  | SoAd | As an intermediate module between TcpIp and DoIP, It is interface between the socket of the TCP / IP stack and the AUTOSAR communication service module.
35 |  | EthIf | It acts as an interface between the Ethernet hardware (transceiver) and the upper layer.
36 |  | EthSM | It manages the communication status of the Ethernet cluster and is responsible for shutdown or startup.
37 |  | EthTrcv | The role of separating actual physical hardware of Ethernet from upper EthIf (development by device).
38 |  | TcpIp | Internet communication module according to IETF(Internet Engineering Task Force). (new)
39 |  | UdpNm | Manage network mode (bus-sleep mode and normal mode) using TcpIp.
40 |  | SD | Module that provides service and search (SOME-IP) between other ECUs in the vehicle network and controls the transmission of event messages.
41 |  | EthSwt | Module that connects multiple physical interfaces by controlling an Ethernet switch through an Ethernet driver or SPI. Depends on external device.
42 |  | SomeIpXf | Module for serializing or deserializing SOME / IP data.
43 |  | SomeIpTp | Module that continuously sends / receives large capacity SOME / IP data.
44 | J1939 | J1939Tp | Specs used in Truck and Trailer (same role as CAN Tp).
45 |  | J1939Dcm | Diagnostic communication control processing based on DM (Diagnostic Message) message of commercial vehicle communication.
46 |  | J1939Nm | Module that controls the network SLEEP synchronization of J1939 communication channels.
47 |  | J1939Rm | Diagnosis request management module based on commercial vehicle communication DM message.
48 | SEC | Cal | Library form. Provides encryption related functions (keys, data encryption / decryption, random number generation, etc.).
49 |  | Csm | This module provides functions (keys, data encryption / decryption, random number generation, etc.). related to encryption and supports synchronous / asynchronous method.
50 |  | SecOC | Additional function of MAC(Message Authentication and Verification) for security enhancement of CAN communication.
51 |  | Crc | Library form. A module that calculates the CRC to check if it is valid data.
52 |  | E2E | End-To-End Protection. A module that protects and verifies faults in Safety related data element transmitted via RTE using CRC control data.
53 |  | E2EXf | Module for applying E2E (End to End Protection) function of Ethernet communication data. Detect communication data corruption.
54 |  | RamTst
2. Non-Standard BSW Modules
| Category | Module
1 | IO | IoHwAb | Effectively managing the functions of the IO module. (Including Mux / Demux support) - by each MCU.
2 |  | MuxDemuxIf
3 |  | OCU | Output Compare Unit, Timer interlocked external pin manipulation processing module.
4 | COM | OsekNm | HKMC Body Domain CAN Network Management Standard Specification.(AUTOSAR NM can not be used)
5 |  | UART | General purpose asynchronous communication function (RS232) - By each MCU
6 |  | CDD_Router
7 | SYS | PM | Entry-and-exit management for MCU low-voltage mode. When MCU is low voltage, it performs tasks such as application operation control and wakeup condition judgment.
8 |  | CoSvAb | Using the HW Timer inside the MCU, At the time interval expired required by the Application and IoHwAb modules, It executes the function of generating an event to the relevant module through a timer interrupt.
9 | SEC | CtrlRAM | Protected RAM data management and fault detection.
10 |  | RegMon | Monitoring the specific MCU Register, Shoud be replace with CorTst(MCAL)
11 |  | RomTst | Checking the completeness of the ROM code/data
12 | OS | Imp_Os | Additional feature of OS (CPU Load, Exception Handle, OS Profile)
3. HMC Specific Modules
| Category | Module
1 | CAN | CanCM | As a feature of XENON SWP CAN Station Manager, It monitors the vehicle battery voltage and manages transmission and reception of CAN network according to voltage level.
2 | COM | EthDiag | Adaptation module for ethernet diagnostic with can diagnostic tools
3 | SEC | IdsM | Manager for the intrusion detection system for CAN network (range / frequency check)
4. Indivisual SW Solution
| Category | Module
1 | FBL | FBL | MCU initialization and Flash Programming function (MCU-specific, Secure Access / Flash supported) - By each MCU
2 | SEC | HSM | Hardwoare Security Module software